## System Overview (hidden)
System Overview — Conveyor-Fed Automatic PCB Test Station
┌─────────────────────────────────────────────────────────────────────────────────────────────────┐
│ CONVEYOR-FED AUTOMATIC PCB TEST STATION — SYSTEM OVERVIEW │
└─────────────────────────────────────────────────────────────────────────────────────────────────┘
[UPSTREAM CONVEYOR] ──► [ENTRY STOPPER ↑] ──► [BARCODE SCANNER] ──► [PRESS STATION] ──► [EXIT]
│
┌──────────┴──────────┐
│ PNEUMATIC PRESS │
│ (Top plate + pogo │
│ pin carrier down) │
│ + Connector plug-in │
└──────────┬──────────┘
│
┌──────────┴──────────┐
│ TEST INSTRUMENTS │
│ • KIKUSUI PWR401L │
│ • Lauterbach Trace32│
│ • PCAN-USB (CAN) │
│ • PLIN-USB (LIN) │
└──────────┬──────────┘
│
┌──────────┴──────────┐
│ TEST PC │
│ orchestrator.py │
│ gui_main.py │
│ MySQL logging │
│ HTML report │
└──────────┬──────────┘
│
PASS ◄───────────────┼───────────────► FAIL
│ │
[EXIT CONVEYOR] [REJECT TRAY]

## Flow Diagram (hidden)
XNF FCT AUTOMATION — FULL SYSTEM DESIGN & FLOW DIAGRAM
Product: RH_i460 NFC/NON-NFC ¦ Config: 2 Fixtures × 4 Slots = 8 PCBs/cycle ¦ Base FCT: NFC_Rev3.01 ¦ Date: 2026-06-09
① MATERIAL INPUT
[5 empty] | INPUT TRAY STACK MAGAZINE |  |  |  | • 16 PCBs per tray (8×2 layout) • Multiple trays stacked vertically • Motorised elevator lifts tray to pick level • Separate input magazines for NFC / NON-NFC variants
[6 empty] | ↓ | Robot lifts top tray to pick area
[5 empty] | ROBOT ARM + GRIPPER |  |  |  | • 6-axis / SCARA robot • 4-finger or vacuum cup gripper • Picks 2 or 4 PCBs per cycle (TBD) • Repeatability target: ±0.1 mm
↓
② ALIGNMENT & 2D BARCODE SCAN
◄ | ALIGNMENT JIG |  |  | ←→ | • Robot places 4 PCBs onto alignment JIG • 1 scanner reads all 4 × 2D codes simultaneously • Barcode IDs linked to slots 1-4 • Scan position: at JIG (per design memo) |  |  | ←→ | 2D BARCODE SCANNER KEYENCE SR-X100W / SR-700
[6 empty] | ↓ | All 4 barcodes read OK?
[5 empty] | DECISION: Barcodes Valid? |  |  | ✗ → FAIL: robot moves to fail tray
↓
③ FIXTURE LOADING (Robot arm places PCBs)
| FIXTURE 1 Left Type 4 Slots |  |  |  | Robot places 4 PCBs simultaneously into each fixture • Pneumatic actuator closes fixture lid • Pogo pins contact PCB test pads • Fixture type selected: NFC or NON-NFC (Left / Right) • Clamping force: TBD (N) |  |  |  | FIXTURE 2 Right Type 4 Slots
|  |  |  | ←→ |  |  |  | ←→
↓
④ FCT TEST EXECUTION
| PLC (BANWA — Thailand) Signals to FCT PC: → FCT_START ← FCT_READY ← SLOT_PASS[1-4] ← SLOT_FAIL[1-4] ← FCT_DONE ← FCT_ERROR |  |  |  | FCT TEST PC (INDIA — NFC_Rev3.01 updated) • orchestrator.py 4-slot parallel threads • integrated_automation.py • per-slot: T32 + PSU + CAN + LIN • pc_io_interface.py (PLC I/F) • Barcode scanner driver • CSV + HTML result logger • gui_main.py (4-slot display) |  |  |  | TEST INSTRUMENTS (per 4-slot operation) • 4× KIKUSUI PWR401L (PSU per slot, VISA/USB) • 4× Lauterbach Trace32 (PowerDebug E40 + DC20A) • PCAN-USB Pro FD ×2 (4 CAN channels total) • PLIN-USB (LIN interface) • KEYENCE SR-X100W (2D barcode scanner)
|  |  |  | ⇔ |  |  |  | ⇔
↓
④-a TEST SEQUENCE PER SLOT (runs in parallel across all 4 slots)
| HW SETUP T32 connect PSU on | LED RGB on/off voltage verify | BATTERY ADC read voltage check | MOTOR OCP test actuate | EOS offset/zero process | SG 1+2 Strain Gauge OpAmp verify | CAPA Capacitive sensor | NFC read/write verify | CAN bus comm PCAN | LIN bus comm PLIN | RESULT PASS/FAIL CSV+HTML
| → | → | → | → | → | → | → | → | → | →
↓
⑤ RESULT SORTING & OUTPUT
DECISION: Per-Slot PASS / FAIL?
|  |  | ↓ PASS |  |  | ↓ |  |  | ↓ FAIL
| PASS TRAY (OK parts) ✓ Slot result = PASS |  |  |  | ROBOT ARM Removes PCBs from fixture (sorted by slot result) |  |  |  | FAIL TRAY (NG parts) ✗ Slot result = FAIL
|  |  |  | ← |  |  |  | →
⑥ LOOP — Robot picks next batch. Empty tray moved. Full output tray swapped by operator.
LEGEND
| Hardware / Mechanical |  |  | FCT Software (INDIA scope) |  |  | PLC / I/O Signal (BANWA) |  |  | Instruments

## Condition
Base design: |  | Manual handling 1pcs system control (FW, SW)
Modefy points |  | [ Fit for autohandling system ]
Sytem image at sheet " FCT autohandling design memo "
Test four targets simultaneously on a single PC.
|  | CAN / LIN tool |  | at sheet " FCT tool list (Main Equip.) "
2D scanner
add control design for handling machine timming control (PLC)
FCT START trigger
FCT FINISH trigger
OK(PASS) / FAIL sign
ERROR sign
others
data logging extract,
each item CSV file format, (continue html file,continue no problem)
reason: for pick-up our server.

## FCT tool list (Main Equip.)
ITEM | MAKER | MODEL | MEMO
Barcode scanner | KEYENCE | SR-X100 or SR-X100W | USB (USB-COM) type .
or
SR-700
CAN tool | PEAK | PCAN-USB Pro FD | Design debug timing, buy yourself, after we buy it if can.
LIN tool | PEAK | PLIN-USB
PowerSupply | KIKUSUI | PWR401L | VISA control. USB
Debugger | LAUTERBACH | PowerDebug E40 LA-3503 | Debugger tool no change
Debugger Coretex-M (Arm6/7/8) DC20A (PACK) LA-3254
Arm Converter IDC20A to MIPI-10/20D/34 LA-3770
PC set |  |  | 1PC control 4set

## FCT autohandling design memo
PCBAは 8x2 = 16個入りトレイに同じ向きで入っている
トレイは複数個積み上げられている
一番上のトレイを持ち上げて 取り出しエリアにおく
PCBAの取り出しは取り出しエリアにて行う
空トレイになったらトレイを 別の所に置くアクションを行う、
※検査後のトレイ収納も同じ考え方
OK/NGの仕分け
Alignment JIG ( Waiting to INPUT and OUTOUT)
1tray pick-up from stacked. | Arrow are |  |  |  | " Rotation "
| Robot, arm control (image) |  |  |  | 2JIG for INPUT (2_PCBA are on), 2D code scan here
Pick up 2pcs set to alig-JIG |  | Emply (not hold) action |  |  | 2JIG for OUTPUT (Not on PCBA) after FCT 2_PCBA on |  |  | OPEN / CLOSE action
Hold on action
Scan 2D code （1scanner read 4pcs 1time action)
|  | Pick up 1 tray | Set to Ali-JIG
Set to FIxture
Do FCT
Take out from fixture
Down to select stage | [6 empty] | Fixture [2pcs set] x2 set
Design reason for ProbePin fitting and maintenance
Select OK / NG pick-up | [5 empty] | FCT tester, 1PC control to 4pcs
set to finish tray
TRAY
8x2 [pcs]
Pick-up stage
(1-tray set)
Aligment JIG (a)
2 pcs
Aligment JIG (b)
2 pcs
Aligment JIG (c)
2 pcs
Aligment JIG (d) 2 pcs
FCT_tester (Fixture)
INPUT
OUTPUT
FIXTURE
[ BED of NAIL ]
FIXTURE
[ BED of NAIL ]
FIXTURE
[ BED of NAIL ]
FIXTURE
[ BED of NAIL ]
" After " stage (Select stage)
PASS (OK)
FAIL (NG)
NG TRAY
OK TRAY
2D_code acanner (1 scanner read 4 pcs data)

## TQ - India Scope
TECHNICAL QUESTIONS — INDIA TEAM SCOPE (I/F I/O Design + FCT Program Update)
Activity: (1) I/F I/O design [Collaborative INDIA+BANWA] ¦ (2) FCT inspection program update for 4-PCB auto-handling [INDIA solo] ¦ Base code: NFC_Rev3.01
SECTION 1 — I/F I/O SIGNAL DEFINITION (Collaborative: INDIA designs spec, BANWA implements PLC side)
No. | Category | Question | Background / Why needed | Expected Answer Format | Direction | Priority | Answer / Status
1 | Signal List | What is the complete list of signals FCT PC must OUTPUT to PLC? Proposed: FCT_READY, FCT_DONE, SLOT_PASS[1-4], SLOT_FAIL[1-4], FCT_ERROR | Defines PLC input module wiring. INDIA must propose list; BANWA must accept it. | Signal name list + direction + logical state | INDIA→BANWA | HIGH
2 | Signal List | What is the complete list of signals FCT PC must RECEIVE from PLC? Proposed: FCT_START, PCB_IN_SLOT[1-4], FIXTURE_CLOSED | Defines which PLC output signals trigger FCT software actions. | Signal name list + direction + trigger condition | BANWA→INDIA | HIGH
3 | Granularity | Are PASS/FAIL signals per-slot (4 individual signals) or per-fixture (one combined signal after all 4 PCBs done)? | Per-slot allows PLC to release each slot independently after its test. | Decision: per-slot OR per-fixture | BANWA decide | HIGH
4 | Physical I/F | What physical interface carries signals between test PC and PLC — USB-relay, PCIe I/O card, or Ethernet protocol (Modbus TCP / EtherNet/IP)? | Choice drives Python driver library selection. | Interface type + model/protocol | BANWA propose | HIGH
5 | Voltage Level | Signal voltage level: 24 V DC (industrial standard) or 5 V DC (PC GPIO)? | If 24 V: USB-relay or optocoupler isolation needed. Affects INDIA hardware spec. | Voltage level (V DC) + sink/source type | BANWA | HIGH
6 | Timing: START | What is the minimum FCT_START pulse width (ms) the FCT PC must detect? Minimum hold time before PCB confirmed seated? | Python polling interval must be ≤ half minimum pulse width to ensure reliable detection. | Numeric: pulse width ms + hold time ms | BANWA define | HIGH
7 | Timing: DONE | How long must FCT_DONE (PASS/FAIL) stay asserted so PLC scan cycle can read it reliably? | PLC scan cycle time determines minimum hold time needed. | Numeric: hold time ms | BANWA define | MED
8 | Handshake | Is a handshake required? E.g. PLC→FCT_START → FCT PC asserts FCT_ACK → PLC releases FCT_START → test begins? | Without handshake, PLC pulse shorter than Python poll interval may be missed. | Protocol description or state machine sketch | Agree together | HIGH
9 | ERROR Recovery | After FCT_ERROR, what PLC action — pause robot, wait for manual clear, or auto-retry? What signal clears the error from FCT PC? | Prevents robot placing next PCB into an error slot. | Recovery sequence description | BANWA decide + INDIA implement | HIGH
10 | READY Signal | Should FCT PC send FCT_READY to PLC when software is fully initialised and waiting? | PLC must not send FCT_START before Trace32/PSU/PCAN are ready. | Yes/No + signal behaviour | Agree together | MED
11 | Barcode Data Path | Does 2D scanner (KEYENCE SR-X100/SR-700) connect directly to FCT test PC via USB, or does PLC read barcode and pass ID to FCT PC via shared register? | Current NFC_Rev3.01 already has scan_code field. Direct USB-to-PC is simplest. | Decision: direct USB to FCT PC OR via PLC data channel | Agree together | HIGH
12 | Slot Identity | How does FCT PC map each scanned barcode to a fixture slot (1-4) — slot-ID encoding in START trigger, or scanning order = slot order? | Needed to correctly label each result row in the CSV with the right barcode ID. | Slot-ID encoding scheme or scan order convention | Agree together | HIGH
13 | I/O Spec Doc Owner | Who owns the I/O Signal Interface Specification document — INDIA drafts + BANWA reviews, or BANWA drafts + INDIA reviews? | Must be baselined before BANWA's PLC program starts (schedule: '26_7). | Ownership decision | BANWA/INDIA | MED
14 | 2 Fixture Types | Both fixture types (Left/Right or NFC/NON-NFC) — do they share the same FCT_START/DONE signals, or each has independent signal set? | Affects total I/O count and whether FCT SW needs to know active fixture type. | Shared or independent signal sets per fixture type | BANWA define | MED
SECTION 2 — FCT INSPECTION PROGRAM: 4-PCB PARALLEL ARCHITECTURE (INDIA solo — base NFC_Rev3.01)
No. | Category | Question | Background / Why needed | Expected Answer Format | Direction | Priority | Answer / Status
15 | Architecture | 4-slot parallel: use (a) 4 independent Python processes (each with own Trace32/PSU/PCAN) or (b) one process with 4 threads sharing controllers? | Option (a) is isolated; option (b) is lighter but needs thread-safe orchestrator.py refactor. | Decision: multi-process OR multi-thread | INDIA decide | HIGH
16 | T32: Multi-Probe | Does the Lauterbach setup support 4 simultaneous debug connections? Current: 1x PowerDebug E40 + DC20A. If 4-PCB parallel flash needed: 4 probes + 4 licenses required. | If sequential flash is acceptable, one probe with time-multiplexed connections reduces hardware cost. | Simultaneous (4 probes) OR sequential flash (1 probe) | INDIA verify + Lauterbach | HIGH
17 | T32: Python API | Can Functional/trace32.py be instantiated 4 times simultaneously? Current code uses global t32.dbg. Multi-slot needs per-slot Trace32Interface with separate port numbers. | Core dependency for parallel execution architecture. | Yes/No + required changes to trace32.py | INDIA verify | HIGH
18 | PSU: Per-slot | Max current per RH_i460 PCB under test (A)? Can 1x KIKUSUI PWR401L (40 V / 1 A) supply all 4 PCBs? Or 1 PSU per slot = 4 units? | 4 PSUs need 4 VISA addresses. Significant cost impact. | Max current per PCB (A) + decision: shared or 4 units | INDIA verify HW spec | HIGH
19 | PCAN Channels | How many CAN channels does one RH_i460 PCB use during FCT? PCAN-USB Pro FD has 2 CAN FD channels — how many units needed for 4 PCBs? | Determines PCAN hardware procurement quantity. | CAN ch per PCB + total PCAN units needed | INDIA verify test spec | HIGH
20 | PLIN Channels | How many LIN channels per PCB during FCT? Can PLIN-USB time-multiplex 4 PCBs or is 1 unit per PCB needed? | Determines PLIN hardware qty. | LIN ch per PCB + total PLIN units needed | INDIA verify test spec | HIGH
21 | Variant per Slot | Can each slot independently select NFC (preset=2) or NON-NFC (preset=1), or must all 4 slots run same variant per batch? | Mixed-variant batches need per-slot variant selection in GUI and per-slot Trace32 script. | Same variant per batch OR independent per slot | INDIA + production | MED
22 | Start Trigger | In automated mode, what triggers FCT test start — PLC FCT_START signal (removing GUI Play button) or still GUI button? | If PLC-triggered: automation loop must watch I/O signal instead of GUI input. | PLC signal-triggered OR GUI-triggered | INDIA + BANWA | HIGH
23 | Sequence Changes | Which test steps in NFC_Rev3.01 (LED/BAT/Motor/EOS/SG/CAPA/NFC/CAN/LIN) need modification for automated fixture? E.g. CAPA test uses DigitalSwitchController — how is physical switch press automated? | CAPA step requires a physical capacitive switch actuation. Must be verified if auto fixture covers this or if test step needs change. | List of steps needing modification + proposed solution | INDIA review + BANWA | HIGH
24 | Test Duration | What is the measured end-to-end test time per PCB using NFC_Rev3.01 NORMAL timing profile? (Reference: supply_on=5s, bat_wait=5s, sg_measure=3s×2 → rough estimate ~60-90s?) | Required to calculate takt time and confirm 4-slot parallel meets production target. | Measured duration (s) in NORMAL profile | INDIA measure | HIGH
25 | Power Cycle | Between successive PCBs in the same slot, is a full PSU power cycle (supply_off=2s + supply_on=5s = ~7s) mandatory, or can it be skipped if the slot is already initialised? | Optimising this 7s saves ~7s per PCB per slot. High impact on takt. | Mandatory per-PCB cycle OR can skip on re-run | INDIA review | MED
SECTION 3 — DATA LOGGING & RESULT FORMAT (INDIA solo)
No. | Category | Question | Background / Why needed | Expected Answer Format | Direction | Priority | Answer / Status
26 | CSV Fields | Required fields in per-PCB CSV: Barcode ID, Slot No., Date-Time, Variant, each test item (measured + PASS/FAIL), overall PASS/FAIL? | Production server picks up CSV files. Field list must match server expectations. | CSV column list / sample row | INDIA + production | HIGH
27 | File Naming | Naming convention for result CSV files? Suggestion: YYYYMMDD_HHMMSS_<BarcodeID>_Slot<N>_<PASS¦FAIL>.csv | Server-side automation may depend on filename pattern. | File naming pattern | INDIA + production | MED
28 | MySQL | Is MySQL logging (in System Overview sheet) a firm requirement, or is CSV-only sufficient per Condition sheet? | MySQL adds ~2 days effort. Needs explicit YES/NO decision. | YES or NO | U-Shin decision | MED
29 | HTML Report | Should HTML report be per-PCB (current) or a combined 4-slot batch report? | Combined report more useful for operators but requires redesigning html_report_generator.py. | Per-PCB OR 4-slot combined | INDIA decide | MED
30 | Log Storage | Result files written to local PC path or network share on factory server? | If network share: UNC path must be available with write permission from test PC. | Path specification | Production team | MED
SECTION 4 — SCHEDULE & DELIVERABLES (INDIA planning)
No. | Category | Question | Background / Why needed | Expected Answer Format | Direction | Priority | Answer / Status
31 | I/F Spec Date | By what date must I/O Signal Interface Specification be finalised? (PLC program starts '26_7 — INDIA I/F design: 2-3 wks from '26_6) | BANWA cannot start PLC program until I/F is agreed. | Target date (YYYY-MM) | INDIA + BANWA | HIGH
32 | FCT Review Scope | FCT review = 2 months' — does this include validation on real PCBs with the new fixture, or only code update? | 2 months is tight if it includes on-site fixture integration. Scope must be defined. | Scope description + acceptance criteria | INDIA + HMM-HQ | HIGH
33 | Integration Test | Who conducts end-to-end integration test — INDIA on-site in Thailand or remote support with BANWA leading? | On-site is recommended for debugging I/F timing issues. | On-site / remote / BANWA-led | BANWA + INDIA | MED
34 | Acceptance Criteria | Acceptance criteria for updated FCT software — e.g. zero false-PASS rate, ≥99% barcode traceability, test time within takt? | Required to formally close 'FCT review' schedule item. | Acceptance criteria list | U-Shin / HMM-HQ | MED

## Quotation - India
QUOTATION REQUEST — INDIA TEAM SCOPE: I/F I/O Design + FCT Inspection Program Update
Prepared by (INDIA): | Charan Singh / INDIA team |  |  | Project: | XNF FCT Auto-Handling — INDIA activities only
Date: | 2026-06-09 |  |  | Doc No.:
Base FCT Code: | NFC_Rev3.01 |  |  | PCB Model: | RH_i460 NFC + NON-NFC
Schedule Ref.: | XNF FCT Automation Schedule 260602a — INDIA rows only |  |  | Target: | 4-PCB parallel, 2 fixture types
Rev.: | 0 |  |  | Status: | DRAFT — pending TQ answers
SCOPE: | INDIA software activities ONLY. Excluded: hardware, robot arm, PLC program (BANWA/outsource scope).
PHASE 1 — I/F I/O SIGNAL DESIGN (Collaborative: INDIA leads spec) ¦ Schedule: 2-3 weeks starting '26_6
Item | Work Item / Deliverable | Scope Description | Days | Unit | Rate | Total | Remarks / Dependencies
1-01 | I/O Signal Interface Spec Document | Define all signals: names, direction, voltage, timing, handshake protocol between FCT PC and PLC (both fixture types). Agree with BANWA before their PLC program starts. | 3 | Doc | TBD | TBD | Critical input to BANWA PLC design. Must be done before '26_7.
1-02 | Signal Verification Test Plan | Define loopback test + timing verification plan to confirm correct I/O signal behaviour once BANWA PLC side is ready. | 1 | Doc | TBD | TBD | Joint test with BANWA after PLC program is ready
1-03 | Python I/O Driver (pc_io_interface.py) | Implement Python driver for chosen physical interface (USB-relay / Modbus TCP — TBD per Q4/Q5). API: wait_for_start(slot), send_pass(slot), send_fail(slot), send_error(slot), send_ready(). | 3 | Lot | TBD | TBD | Depends on Q4 (interface type) and Q5 (voltage level) answers
1-04 | I/O Integration Test with BANWA PLC | Joint session: verify all signals trigger correct PLC actions. Debug timing issues. Remote or on-site per Q33 decision. | 2 | Lot | TBD | TBD | Needs BANWA PLC program ready first
PHASE 2 — FCT INSPECTION PROGRAM CORE UPDATE (INDIA solo — 4-slot parallel) ¦ Part of 2-month FCT review
Item | Work Item / Deliverable | Scope Description | Days | Unit | Rate | Total | Remarks / Dependencies
2-01 | 4-Slot Parallel Execution Architecture | Refactor orchestrator.py + integrated_automation.py for 4 concurrent test threads/processes. Thread-safe resource allocation for Trace32, PSU, PCAN, PLIN per slot. Slot management + per-slot state machine. | 5 | Lot | TBD | TBD | Core change. Depends on Q15 (arch decision) and Q17 (T32 API)
2-02 | Lauterbach Multi-Probe Management | Update Functional/trace32.py + HardwareSetupVerifier for 4 independent Trace32 instances (per-slot port numbers, separate script sessions, connect/go/disconnect per slot). | 4 | Lot | TBD | TBD | Depends on Q16 (probe count) and Q17 (API verification)
2-03 | PSU Per-Slot Control (4 VISA instances) | Update power_supply.py for 4 KIKUSUI VISA addresses. Each slot gets independent supply on/off/measure. Handles supply_on_wait (5s) and supply_off_wait (2s) per slot. | 2 | Lot | TBD | TBD | Straightforward if 4 separate PSU units confirmed (Q18)
2-04 | PCAN + PLIN Per-Slot Channel Assignment | Update can_service.py / lin_service.py to bind each slot to its PCAN channel (slot1→ch1, slot2→ch2, etc.) and PLIN port. Validate with 4-PCB simultaneous CAN/LIN traffic. | 3 | Lot | TBD | TBD | Depends on Q19 and Q20 channel count answers
2-05 | PCB Variant Auto-Selection per Slot | Extend GUI and automation runner to accept NFC/NON-NFC variant assignment per slot. Passes correct Trace32 preset (1 or 2) to each slot thread independently. | 2 | Lot | TBD | TBD | Depends on Q21 (variant-per-slot decision)
2-06 | PLC Start Trigger Integration | Replace GUI Play-button trigger with PLC FCT_START signal listener. Slot test starts when pc_io_interface (1-03) detects FCT_START for that slot. | 2 | Lot | TBD | TBD | Depends on 1-03. Q22 must confirm PLC-triggered mode.
2-07 | CAPA Test — Auto Fixture Adaptation | Verify/adapt DigitalSwitchController for automated fixture. If physical capacitive switch is actuated by fixture mechanism, confirm signal path. Update test step if behaviour changes. | 2 | Lot | TBD | TBD | Q23 — must test on real auto fixture. Risk item.
2-08 | Per-Slot PASS/FAIL Signal Output | After each slot completes test, call send_pass(slot)/send_fail(slot) via pc_io_interface so PLC can release that slot to the pass/fail sorter. | 1 | Lot | TBD | TBD | Quick integration once 2-01 and 1-03 are done
PHASE 3 — BARCODE SCANNER INTEGRATION + DATA LOGGING (INDIA solo)
Item | Work Item / Deliverable | Scope Description | Days | Unit | Rate | Total | Remarks / Dependencies
3-01 | Barcode Scanner Driver | KEYENCE SR-X100/SR-700 USB-COM serial reader in Python. Map each scanned 2D code to its fixture slot. Trigger scan at correct point in test flow. | 2 | Lot | TBD | TBD | Depends on Q11 (data path), Q12 (slot mapping), Q13 (scanner model)
3-02 | Per-Slot CSV Result Logger | Per-PCB CSV with: barcode ID, slot no., variant, date-time, all test items (measured + PASS/FAIL), overall PASS/FAIL. File naming per agreed convention. | 2 | Lot | TBD | TBD | Depends on Q26 (fields) and Q27 (naming convention)
3-03 | HTML Report Update | Update html_report_generator.py for combined 4-slot batch report OR confirm per-PCB report is sufficient. | 1 | Lot | TBD | TBD | Depends on Q29 decision. Low effort either way.
3-04 | MySQL Logging Module (conditional) | If Q28=YES: implement MySQL INSERT per test result row with barcode traceability. Connection pooling, error handling. | 2 | Lot | TBD | TBD | CONDITIONAL — only if confirmed required. Not in base total.
PHASE 4 — GUI UPDATE + SYSTEM TESTING + DOCUMENTATION
Item | Work Item / Deliverable | Scope Description | Days | Unit | Rate | Total | Remarks / Dependencies
4-01 | 4-Slot Status GUI (gui_main.py) | Update GUI to show 4 independent slot panels: scan code input, test progress, per-test status, PASS/FAIL indicator. All 4 running simultaneously. | 3 | Lot | TBD | TBD | Lower priority — implement after core test logic is stable
4-02 | System Integration & Timing Verification | End-to-end test of all 4 slots simultaneously. Verify I/O timing, barcode traceability, CSV output, PASS/FAIL sorting signal. On-site or remote per Q33. | 3 | Lot | TBD | TBD | Requires BANWA fixture + PLC to be ready
4-03 | Acceptance Test Execution | Run official acceptance batch (agreed PCB count + scenario coverage) with production team. Document results, obtain sign-off for 'FCT review' milestone. | 2 | Lot | TBD | TBD | Final milestone closure
4-04 | Software Design Document Update | Update SDD to reflect 4-slot architecture, I/O driver design, new data logging flow, and any test sequence changes. | 2 | Doc | TBD | TBD | Required project deliverable
EFFORT SUMMARY (BASE ESTIMATE)
Phase 1 — I/F I/O Signal Design |  |  | 9 | Excl. BANWA PLC implementation
Phase 2 — FCT Core (4-slot parallel) |  |  | 21 | Largest block; depends on TQ architecture answers
Phase 3 — Barcode + Data Logging |  |  | 5 | +2 days if MySQL required (item 3-04)
Phase 4 — GUI + Testing + Documentation |  |  | 10
TOTAL (base, excl. MySQL) |  |  | 45 | ~
SCOPE BOUNDARY NOTES:
1. EXCLUDED: hardware (fixtures/robot/conveyor/tray handlers), PLC program (BANWA scope), Lauterbach/PCAN/PLIN hardware purchases, KEYENCE scanner purchase.
2. All estimates in working days (1 engineer). Final figures after TQ-India answers received.
3. Item 3-04 (MySQL) conditional — add 2 days if confirmed YES (Q28).
4. Phase 2 assumes 4x Lauterbach probes + 4x PSU available before integration testing starts.
5. Travel cost for on-site integration test in Thailand (item 4-02) NOT included — quote separately.
6. Items 1-04 and 4-02 require BANWA PLC program to be ready before INDIA can complete them.

## Technical Questions
FCT AUTOMATION — TECHNICAL QUESTIONS FOR VENDOR / ENGINEERING TEAM (FULL AUTOMATION SCOPE)
SECTION 1 — FIXTURE DESIGN
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
1 | Fixture Design | What are the exact PCB outer dimensions (L x W x H) and mounting-hole positions for the auto fixture? | Fixture tray pocket and pogo-pin carrier must be designed to these dimensions. | Drawing or dimension table (mm) | HIGH | U-Shin
2 | Fixture Design | Is the new auto fixture for NFC PCB, NON-NFC PCB, or will it cover both variants? (Slide mentions '2 types fixtures — Left / Right type') | The slide mentions '2 types fixtures for Left type / Right type'. Clarify if NFC vs NON-NFC or Left/Right orientation. | One of: NFC only / NON-NFC only / Both variants | HIGH | U-Shin
3 | Fixture Design | What is the number, layout, and pitch of pogo pins per fixture slot? | Required to confirm Lauterbach/CAN/LIN/power contact reliability at the fixture. | Pin layout drawing and pin count | HIGH | Vendor
4 | Fixture Design | What actuator type closes the fixture — pneumatic cylinder, servo, or other? What is the specified clamping force (N) and stroke (mm)? | Pneumatic drive needs air pressure spec; servo needs torque spec. Critical for fixture open/close timing in PLC program. | Actuator spec sheet + force/stroke values | HIGH | Vendor
5 | Fixture Design | What is the required fixture open/close cycle time (seconds)? | Determines whether robot arm wait time is the bottleneck or the test time. | Numeric: target cycle time in sec | MED | Vendor
6 | Fixture Design | Does each of the 4 PCB slots in a fixture have independent electrical isolation, or are they bussed together? | If bussed, single power supply may suffice. If isolated, 4 x KIKUSUI PWR401L required. | Schematic or written description | HIGH | Vendor
SECTION 2 — ROBOT ARM / HANDLING
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
7 | Robot Arm / Handling | What robot arm model (6-axis / SCARA / delta) and maker is planned for the pick-and-place operation? | Robot reach, payload, and I/O protocol must be matched with alignment JIG and fixture. | Robot model number and spec sheet | HIGH | Vendor
8 | Robot Arm / Handling | What end-effector / gripper type is used — vacuum suction cup or mechanical 4-finger gripper? | Slide shows '4-finger (or other idea)'. Vacuum requires compressor; finger gripper needs PCB edge clearance on tray. | Gripper model/sketch + grip method | HIGH | Vendor
9 | Robot Arm / Handling | How many PCBs does the robot arm pick up and place per cycle — 1, 2, or 4? (Memo shows 'Pick up 2 pcs set to align-JIG') | Memo shows 'Pick up 2 pcs set to align-JIG'. Slide note says 'It's not always four'. Confirm the designed-in count. | Numeric: pcs per cycle | HIGH | U-Shin/Vendor
10 | Robot Arm / Handling | What is the robot-to-fixture placement repeatability spec (mm)? | If worse than ±0.2 mm the pogo pins may miss PCB test pads. | Numeric: ±X mm | HIGH | Vendor
11 | Robot Arm / Handling | How many input trays and how many stacked levels are supported? | Determines magazine/tray handler design and operator replenishment frequency. | Numeric: trays per stack, total PCB capacity | MED | Vendor
12 | Robot Arm / Handling | Is the tray handler integrated into the robot arm motion, or is it a separate conveyor/elevator mechanism? | Impacts overall footprint and PLC I/O count. | Architecture sketch or written description | MED | Vendor
SECTION 3 — 2D BARCODE SCANNER
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
13 | 2D Barcode Scanner | Is the KEYENCE SR-X100W (wide) or SR-700 model selected? What is the USB interface — USB-HID (keyboard emulation) or USB-COM (serial)? | Tool list shows 'USB (USB-COM) type'. Confirm to set up serial port in test PC software. | Model + interface type | HIGH | Vendor
14 | 2D Barcode Scanner | Can one scanner read all 4 PCB 2D codes in a single scan, or does the robot present each PCB separately to the scanner? | Slide: '1 scanner read 4 pcs 1 time action'. If simultaneous, scanner FOV must cover 4 codes. | Simultaneous 4 OR sequential 1-by-1 | HIGH | Vendor
15 | 2D Barcode Scanner | Where is the scan position in the workflow — on the tray, at the alignment JIG, or inside the fixture? | Memo states 'Scan 2D code at Alignment JIG section (idea)'. Confirm final decision. | Location sketch / description | MED | U-Shin
16 | 2D Barcode Scanner | What 2D code symbology is printed on the PCB — QR Code, Data Matrix, or other? | Scanner setting and reader library must match the code type. | Symbology name | MED | U-Shin
17 | 2D Barcode Scanner | How does a missing or unreadable barcode get handled — alarm, skip, or auto-reject to fail tray? | Must be defined in both PLC logic and FCT software. | Procedure description | MED | U-Shin
SECTION 4 — PLC / I/O INTERFACE
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
18 | PLC / I/O Interface | What PLC brand and model is planned (e.g. OMRON, Mitsubishi, Siemens, Keyence KV)? | Determines available communication protocols (Ethernet/IP, Modbus TCP, CC-Link, digital I/O). | PLC model number | HIGH | Vendor
19 | PLC / I/O Interface | What signal voltage level is used for I/O between the PLC and the test PC — 24 V DC, 5 V DC, or relay contact? | Test PC GPIO or USB-relay module must match PLC output rating. | Voltage level (V DC) + current sink/source capability | HIGH | Vendor
20 | PLC / I/O Interface | What is the exact list of I/O signals required between PLC and test PC per fixture? (FCT_START trigger, FCT_FINISH trigger, OK/PASS, NG_FAIL, ERROR sign, others) | The Condition sheet lists: FCT START trigger, FINISH trigger, OK/FAIL sign, ERROR sign, others. Full list needed for I/O module selection. | Signal list with direction (PLC→PC / PC→PLC) and type | HIGH | U-Shin/Vendor
21 | PLC / I/O Interface | What is the communication protocol between test PC and PLC — digital I/O card, USB relay, Modbus TCP, or Ethernet/IP? | Python test software needs the correct driver/library to be selected. | Protocol name and connection method | HIGH | Vendor
22 | PLC / I/O Interface | What are the timing tolerances for FCT START and FINISH trigger signals (ms)? | Test orchestrator needs to know minimum pulse width to detect the signal reliably. | Numeric: pulse width ms, hold time ms | MED | Vendor
SECTION 5 — TEST PC / SOFTWARE (4-PCB PARALLEL)
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
23 | Test PC Software | The current test program is designed for 1 PCB at a time. Will automation require 4 independent instances of the program running in parallel, or one instance managing 4 slots? | Architecture decision affects Lauterbach license count, COM port assignments, and database logging. | One of: 4 instances / 1 multi-thread instance | HIGH | U-Shin
24 | Test PC Software | How many Lauterbach Trace32 licenses and hardware debug probes are required for 4-PCB parallel firmware flashing/testing? | Current setup: 1x PowerDebug E40 + DC20A pack. If 4 PCBs in parallel each need a debug session, 4 probes needed. | Count of probes + license type | HIGH | U-Shin/Lauterbach
25 | Test PC Software | Can PCAN-USB Pro FD supply 4 independent CAN channels simultaneously (4 PCBs tested in parallel)? | PCAN-USB Pro FD has 2 CAN FD channels. May need 2 units for 4 PCBs, or network topology change. | Channel count and hardware qty required | HIGH | U-Shin
26 | Test PC Software | Is one KIKUSUI PWR401L per PCB required (4 units total), or can one unit power all 4 PCBs with current sharing? | Max current per PCB vs. PWR401L capacity. Affects procurement cost significantly. | Power budget per PCB (V, A) + PSU qty | HIGH | U-Shin
27 | Test PC Software | If one PCB fails a test step in the middle of a 4-PCB parallel run, should: (a) stop only that slot and continue other 3, or (b) stop all 4? | Affects test flow logic and PLC signalling for individual fixture release. | One of: (a) per-slot stop / (b) all stop | HIGH | U-Shin
28 | Test PC Software | What data logging format is required — CSV (per Condition sheet), HTML report, MySQL DB, or all three? | Condition sheet states CSV as primary. MySQL is in System Overview but not Condition sheet. | Explicit list of required output formats | MED | U-Shin
29 | Test PC Software | Should the barcode ID scanned at the alignment JIG be written into the test result record (CSV / DB) as the unit identifier? | Traceability requirement from production side. | Yes / No | MED | U-Shin
SECTION 6 — THROUGHPUT
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
30 | Throughput | What is the current single-PCB test time (start to finish, seconds)? | Needed to calculate takt time and assess whether 4-fixture parallel testing meets production target. | Numeric: seconds | HIGH | U-Shin
31 | Throughput | What is the target production takt time per PCB (units per hour)? | Determines number of automation lines and shift planning. | Numeric: pcs/hour | HIGH | U-Shin/Production
32 | Throughput | Is firmware flashing (Lauterbach) performed inside the automated fixture, or in a separate pre-process step? | Flash time can dominate takt. If flash is inside FCT fixture, fixture utilisation drops significantly. | One of: inside FCT / separate step | HIGH | U-Shin
SECTION 7 — SAFETY / INSTALLATION
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
33 | Safety / Installation | What safety standards must the automation cell comply with (e.g. ISO 10218, CE, local Thai factory safety rules)? | Determines safety light curtains, fencing, emergency stop requirements. | Standard names / certificate list | MED | Vendor
34 | Safety / Installation | What are the installation site constraints — floor area (m²), ceiling height, power supply (voltage/phase/ampere)? | Needed for mechanical layout and electrical panel design. | Site spec sheet or measurements | MED | Vendor
35 | Safety / Installation | What compressed air supply is available at the installation site (pressure bar, flow L/min)? | Pneumatic fixture actuators and possibly vacuum gripper require compressed air. | Numeric: bar available, outlet size | MED | Vendor

## Quotation
FCT AUTOMATION HANDLING SYSTEM — QUOTATION REQUEST (FULL AUTOMATION SCOPE)
Requested by: | U-Shin (Thailand) Ltd. |  |  | Project: | XNF FCT Auto-Handling System
Date: | 2026-06-09 |  |  | Document No.:
Base Design Ref.: | NFC_Rev3.01 (Manual 1-pcs FCT) |  |  | Target Qty / Fixture: | 4 PCBs per cycle (2 fixtures)
PCB Model: | RH_i460 NFC + NON-NFC variants |  |  | Location: | Thailand Factory
Revision: | 0 |  |  | Status: | DRAFT — Pending technical Q&A
Prepared by: | Charan Singh |  |  | Contact: | charangopala@gmail.com
A. SCOPE OF SUPPLY — HARDWARE
Item No. | Description | Specification / Requirement | Qty | Unit | Unit Price (THB) | Total Price (THB) | Lead Time (wks) | Remarks
A-01 | Auto FCT Fixture Unit (Left-type) | 4-slot pneumatic press, pogo-pin carrier. Designed for RH_i460 PCB layout. | 1 | Set | TBD | TBD | TBD
A-02 | Auto FCT Fixture Unit (Right-type) | 4-slot pneumatic press, mirror layout of Left-type. | 1 | Set | TBD | TBD | TBD
A-03 | Robot Arm + Controller | 6-axis / SCARA pick-and-place. Payload: TBD. Repeatability: ±0.1 mm target. | 1 | Set | TBD | TBD | TBD
A-04 | End-Effector (Gripper) | 4-finger mechanical gripper or vacuum cup array to match PCB size. | 1 | Set | TBD | TBD | TBD
A-05 | Alignment JIG | PCB pre-positioning stage for 2D code scan. 4-slot capacity. | 1 | Set | TBD | TBD | TBD
A-06 | 2D Barcode Scanner — KEYENCE SR-X100W or SR-700 | USB-COM interface. FOV to cover 4 PCBs simultaneously. | 1 | Unit | TBD | TBD | TBD
A-07 | Input Tray Stack Magazine | Capacity: ≥5 stacked trays (16 PCBs/tray = 80 PCBs). Motorised elevator. | 2 | Set | TBD | TBD | TBD
A-08 | Output Tray Sorter (PASS + FAIL lanes) | Separate tray lanes for OK and NG. Capacity: TBD. | 1 | Set | TBD | TBD | TBD
A-09 | PLC + I/O Module | Brand/model TBD. Min I/O: FCT_START, FCT_DONE, PASS, FAIL, ERROR per fixture. | 1 | Set | TBD | TBD | TBD
A-10 | Pneumatic Supply Unit | FRL unit, solenoid valves for fixture actuator. Pressure: TBD bar. | 1 | Set | TBD | TBD | TBD
A-11 | Safety Fencing + Light Curtain | ISO 10218 compliant. Emergency stop included. | 1 | Set | TBD | TBD | TBD
A-12 | Control Panel + HMI | Panel PC or touch HMI for PLC monitoring. 24 V DC panel. | 1 | Set | TBD | TBD | TBD
A-13 | Cable Management / Wiring Duct | All internal wiring, connectors, labelling. | 1 | Lot | TBD | TBD | TBD
A-14 | Mechanical Frame / Base | Welded steel frame with adjustable levelling feet, ESD surface. | 1 | Set | TBD | TBD | TBD
B. TEST INSTRUMENTS (ADDITIONAL FOR 4-PCB PARALLEL)
Item No. | Description | Specification / Requirement | Qty | Unit | Unit Price (THB) | Total Price (THB) | Lead Time (wks) | Remarks
B-01 | KIKUSUI PWR401L Power Supply (additional) | For 1-PSU-per-PCB configuration. 1 unit currently available. | 3 | Unit | TBD | TBD | TBD | Additional units needed if 4 PCBs run independently
B-02 | PCAN-USB Pro FD (PEAK) | 2 CAN FD channels/unit. Need 2 units for 4 PCBs (4 channels total). | 1 | Unit | TBD | TBD | TBD | 1 unit already owned; confirm ch count per PCB
B-03 | PLIN-USB (PEAK) | LIN master per PCB. Confirm if 1 unit can time-multiplex 4 PCBs. | TBD | Unit | TBD | TBD | TBD | Depends on LIN test parallelism decision
B-04 | Lauterbach PowerDebug E40 LA-3503 (additional) | 1 probe per PCB for parallel flash+debug. 1 unit currently available. | 3 | Unit | TBD | TBD | TBD | Additional probes if parallel flash required
B-05 | Lauterbach Trace32 License (multi-target) | Licence upgrade/addition for multi-core/multi-target session. | TBD | License | TBD | TBD | TBD | Confirm with Lauterbach sales
B-06 | USB Hub (Industrial, 7-port) | For barcode scanner, PCAN, PLIN, Trace32 USB connections. | 2 | Unit | TBD | TBD | TBD
B-07 | Relay / GPIO Interface Module (USB) | For FCT_START / FINISH / PASS / FAIL I/O signals to/from PLC. | 2 | Unit | TBD | TBD | TBD | e.g. USB-RLY08 or similar
C. SOFTWARE DEVELOPMENT & ENGINEERING SERVICES
Item No. | Description | Specification / Requirement | Qty | Unit | Unit Price (THB) | Total Price (THB) | Lead Time (wks) | Remarks
C-01 | FCT Software — 4-PCB Parallel Execution | Modify orchestrator.py / test_sequences.py to run 4 independent test threads. Independent Trace32, PCAN, PLIN, PSU instance per slot. | 1 | Lot | TBD | TBD | TBD | Based on NFC_Rev3.01
C-02 | PLC I/O Interface Module | Python driver for PLC I/O: FCT_START trigger receive, PASS/FAIL/ERROR signal output per slot. | 1 | Lot | TBD | TBD | TBD | Protocol TBD per Q18-Q21
C-03 | Barcode Scanner Integration | KEYENCE SR-X100/SR-700 USB-COM driver. Map scanned 2D ID to PCB slot. Write ID to test log. | 1 | Lot | TBD | TBD | TBD
C-04 | 4-PCB Data Logging (CSV + HTML Report) | Per-slot CSV result file with barcode ID, timestamps, all test item results. Combined HTML report. | 1 | Lot | TBD | TBD | TBD | Current single-PCB report as base
C-05 | MySQL Database Integration (Optional) | Log results to central MySQL DB for traceability and SPC. | 1 | Lot | TBD | TBD | TBD | Confirm if required (see Q28)
C-06 | Test Sequence GUI Update | Update gui_main.py to show 4-slot status simultaneously. Per-slot START/STOP/RESULT display. | 1 | Lot | TBD | TBD | TBD
C-07 | PLC Program (Ladder / Structured Text) | Robot arm sequencing, fixture open/close, tray handling, I/O with test PC. Includes safety interlock. | 1 | Lot | TBD | TBD | TBD | BANWA scope / external vendor
C-08 | System Integration & Commissioning | On-site integration test, timing calibration, handoff documentation. | 1 | Lot | TBD | TBD | TBD | At Thailand factory
C-09 | Test Run & Acceptance | Run with production PCBs. Verify PASS/FAIL sorting accuracy. Sign-off protocol. | 1 | Lot | TBD | TBD | TBD
D. COST SUMMARY
Section A — Hardware (Fixture + Robot + Handling) | [5 empty] | TBD
Section B — Test Instruments (Additional) | [5 empty] | TBD
Section C — Software & Engineering Services | [5 empty] | TBD
Contingency (10%) | [5 empty] | TBD
TOTAL (excl. VAT) | [5 empty] | TBD
NOTES:
1. All prices in THB. USD/JPY options available on request.
2. Items marked TBD require answers to Technical Questions sheet before final pricing.
3. Lead times are from order placement and receipt of signed PO.
4. This quotation is valid for 30 days from issue date.
5. Existing test instruments (1x KIKUSUI, 1x PCAN, 1x Trace32) not included in Section B cost.
6. Software items in Section C assume U-Shin provides full FCT test requirements and Lauterbach script access.
7. PLC program (C-07) to be agreed — can be U-Shin internal or external vendor scope.

## Flow - India Scope
INDIA TEAM SCOPE — DETAILED DESIGN: I/F I/O Signal Design + FCT Software Architecture
Activity: (1) I/F I/O signal spec between PLC-BANWA and FCT-PC-INDIA ¦ (2) FCT inspection program update: 4-slot parallel ¦ Base: NFC_Rev3.01
PART A — I/F I/O SIGNAL DESIGN (Collaborative: INDIA designs spec, BANWA implements PLC side)
| PLC — BANWA (Thailand) |  |  |  | I/O | FCT TEST PC — INDIA (NFC_Rev3.01 updated)
| FCT_START |  |  |  | → (PLC to FCT PC) | PLC triggers FCT test start. Pulse width: TBD ms.
| FCT_READY |  |  |  | ← (FCT PC to PLC) | FCT PC signals it is initialised and waiting for PCBs.
| FIXTURE_CLOSED |  |  |  | → (PLC to FCT PC) | PLC confirms fixture pneumatic closure complete.
| BARCODE_DATA / LINK |  |  |  | → or USB direct | Scanned 2D barcode IDs linked to slots 1-4. Path: TBD.
| SLOT_PASS[1] |  |  |  | ← (FCT PC to PLC) | Slot 1 test result = PASS. PLC releases slot 1 PCB.
| SLOT_PASS[2] |  |  |  | ← (FCT PC to PLC) | Slot 2 test result = PASS.
| SLOT_PASS[3] |  |  |  | ← (FCT PC to PLC) | Slot 3 test result = PASS.
| SLOT_PASS[4] |  |  |  | ← (FCT PC to PLC) | Slot 4 test result = PASS.
| SLOT_FAIL[1] |  |  |  | ← (FCT PC to PLC) | Slot 1 test result = FAIL. PLC routes slot 1 PCB to fail tray.
| SLOT_FAIL[2] |  |  |  | ← (FCT PC to PLC) | Slot 2 test result = FAIL.
| SLOT_FAIL[3] |  |  |  | ← (FCT PC to PLC) | Slot 3 test result = FAIL.
| SLOT_FAIL[4] |  |  |  | ← (FCT PC to PLC) | Slot 4 test result = FAIL.
| FCT_DONE |  |  |  | ← (FCT PC to PLC) | All 4 slots complete. Robot arm may open fixture.
| FCT_ERROR |  |  |  | ← (FCT PC to PLC) | FCT software error (T32 fail, PSU fail, etc). PLC holds robot.
Physical Interface: USB-Relay module / Modbus TCP / EtherNet/IP (TBD per Q4, Q5) ¦ Voltage Level: 24 V DC or 5 V DC (TBD per Q5) ¦ Timing: pulse width / hold time TBD per Q6, Q7 ¦ Handshake protocol: TBD per Q8
PART B — FCT SOFTWARE ARCHITECTURE (INDIA solo — 4-slot parallel execution)
| SOFTWARE MODULE HIERARCHY |  |  |  |  | HARDWARE RESOURCE BINDING (per slot)
| ① gui_main.py (4-slot GUI) • Slot 1-4 status panels (scan code, progress, PASS/FAIL) • PLC-triggered start mode (replaces Play button) | [5 empty] | Slot 1 | Slot 2 | Slot 3 | Slot 4
[6 empty] | Trace32 Probe | #1 Port 4711 | #2 Port 4712 | #3 Port 4713 | #4 Port 4714
[6 empty] | PSU (KIKUSUI) | VISA Addr 1 | VISA Addr 2 | VISA Addr 3 | VISA Addr 4
|  |  | ↓ |  |  | PCAN Channel | CAN Ch.1 | CAN Ch.2 | CAN Ch.3 | CAN Ch.4
| ② pc_io_interface.py (PLC I/O driver — NEW) • wait_for_start(slot) → listens for FCT_START[slot] from PLC • send_ready() ← asserts FCT_READY to PLC • send_pass(slot) ← asserts SLOT_PASS[slot] to PLC • send_fail(slot) ← asserts SLOT_FAIL[slot] to PLC • send_error(slot) ← asserts FCT_ERROR[slot] to PLC |  |  |  |  | PLIN Port | COM3 | COM4 | COM5 | COM6
[6 empty] | Trace32 ELF | variant[1] | variant[2] | variant[3] | variant[4]
[6 empty] | Scan Code | barcode[1] | barcode[2] | barcode[3] | barcode[4]
|  |  | ↓ |  |  | CSV File | Slot1_*.csv | Slot2_*.csv | Slot3_*.csv | Slot4_*.csv
| ③ barcode_scanner.py (NEW — KEYENCE SR-X100W USB-COM) • Read 2D codes for slots 1-4 ¦ map scan_code[n] → slot n ¦ pass ID to orchestrator |  |  |  |  | PSU V/I | TBD V/A | TBD V/A | TBD V/A | TBD V/A
[6 empty] | PLC START | FCT_START[1] | FCT_START[2] | FCT_START[3] | FCT_START[4]
|  |  | ↓ |  |  | PLC PASS | SLOT_PASS[1] | SLOT_PASS[2] | SLOT_PASS[3] | SLOT_PASS[4]
| ④ integrated_automation.py (UPDATED — 4-slot orchestration) • Spawn 4 threads (or processes), one per fixture slot • Each thread runs independently: HW setup → test sequence → result • Thread-safe resource allocation (lock per Trace32/PSU/PCAN instance) • is_first_run flag per slot (not global) • Per-slot _canlin_event, _automation_lock • Receives: scan_code[slot], variant[slot], psu_instance[slot] • Calls test_sequences.TestSequenceRunner(slot_adapter) |  |  |  |  | PLC FAIL | SLOT_FAIL[1] | SLOT_FAIL[2] | SLOT_FAIL[3] | SLOT_FAIL[4]
↓
⑤ test_sequences.TestSequenceRunner (per slot instance) • Per-slot adapter: Trace32Interface(port=slot_port), PSU(VISA_addr), PCAN(ch), PLIN(ch) • Sequence: HW_Setup → LED → BAT → Motor → EOS → SG → CAPA → NFC → CAN → LIN
↓
⑥ result_logger.py (UPDATED — per slot CSV + combined HTML) • CSV: BarcodeID, SlotNo, Variant, DateTime, per-test result, PASS/FAIL • HTML: combined 4-slot batch report • MySQL: optional — write per-PCB result row (TBD per Q28)
PART C — FCT TEST SEQUENCE FLOW (per slot, runs in parallel for all 4 slots)
| START (FCT_START from PLC) | HARDWARE SETUP Trace32 connect PSU power on (5 s wait) |  | LED TESTS • RGB on/off cycle • Voltage verify per LED | BATTERY MONITOR • ADC voltage read • Range check |  | MOTOR TESTS • OCP test • Actuation check |  | EOS TESTS • Mode switch • Offset/Zero/Process |  | STRAIN GAUGE • SG1 measure • SG2 flag/reset/measure
| PLC sends start trigger. pc_io_interface.wait_for_start(slot) returns. scan_code[slot] already captured. | connect_trace32(preset=variant) ¦ PSU.on() ¦ supply_on_wait=5.0 s ¦ first_run_fw_init_wait=5.0 s (first run only) |  | led_stabilize_wait=0.5 s / LED ¦ led_off_stabilize_wait=2.0 s ¦ Tests: all LEDs individually | bat_initial_wait=5.0 s ¦ bat_retry_wait=8.0 s ¦ Measured via T32 Var.VALUE() |  | motor_actuate_wait=1.0 s ¦ MotorOCPError handled per slot independently |  | eos_mode_switch_wait=0.2 s ¦ eos_measure_wait=0.4 s ¦ eos_set_process_wait=0.6 s |  | sg1_measure_wait=3.0 s ¦ sg2_measure_wait=3.0 s ¦ Total ~6 s (dominant timing step)
[5 empty] | ↓ (7 more steps — continue below) | [6 empty] | ↓ (continues)
| CAPA TEST • Capacitive sensor • DigitalSwitchController | NFC TESTS • NFC read/write • Data verify |  | CAN TESTS • Bus communication • PCAN-USB Pro FD | LIN TESTS • Bus communication • PLIN-USB |  | RESULT • PASS or FAIL • per slot decision |  | LOG RESULT • CSV per slot • HTML batch report |  | SIGNAL PLC • SLOT_PASS[n] or • SLOT_FAIL[n]
| capa_retry_timeout=3.0 s ¦ RISK: physical switch press needed — verify auto fixture provides actuation | Only for NFC variant (preset=2). Skipped for NON-NFC variant. |  | Per-slot PCAN channel (ch1-4). Verify no cross-talk between 4 active CAN buses. | Per-slot PLIN port. Verify simultaneous LIN traffic on 4 channels. |  | Overall PASS if all steps PASS. Any FAIL = slot FAIL. Error = slot ERROR. |  | CSV: BarcodeID + slot + variant + all test items + overall. HTML: 4-slot combined. |  | pc_io_interface.send_pass(slot) or send_fail(slot). Asserted for hold_time ms (TBD). PLC releases robot arm for that slot.
NOTE: All 4 slots run this sequence simultaneously in parallel threads. Each slot has independent Trace32/PSU/PCAN/PLIN instances. Total test time ≈ single-slot time (no serial overhead). Takt time dominated by longest step (SG: ~6s + BAT: ~5s + PSU on: ~5s = ~16s minimum overhead per slot).

## Why_How_Helper
WHY & HOW HELPER — Technical Traceability for TQ India Scope Questions
Purpose: This sheet explains WHY each TQ exists and HOW answering it enables full 4-PCB automation. Use this to present context to management.
No. | Section | Question (Summary) | WHY — Technical Reason | HOW — Contribution to Full Automation | Key Dependency / Risk | Priority | Direction
SECTION 1 — I/F I/O SIGNAL DEFINITION (Collaborative: INDIA + BANWA)
1 | Sec1 · Signal List | FCT PC Output Signals to PLC | The PLC is the robot's brain — it only moves the arm, opens/closes fixtures, and conveys PCBs based on what FCT PC tells it. Without a defined agreed list of output signals (FCT_READY, FCT_DONE, SLOT_PASS[1-4], SLOT_FAIL[1-4], FCT_ERROR) the PLC programmer cannot wire the input module or write the logic that reacts to test results. This is the very first dependency in the entire automation chain. | Each signal maps to a robot action: SLOT_PASS triggers conveyor release for that slot; SLOT_FAIL routes PCB to reject lane; FCT_ERROR freezes the robot to prevent damage. Defining them now allows parallel hardware procurement (relay cards I/O modules) and PLC programming to begin immediately. | PLC input wiring and program CANNOT start until this list is baselined. Delay here delays BANWA's entire PLC timeline ('26_7). | HIGH | INDIA→BANWA
2 | Sec1 · Signal List | FCT PC Input Signals from PLC | Current NFC_Rev3.01 waits for a human operator to press the GUI Play button. In automation mode the PLC must replace the human — it sends FCT_START when fixture is confirmed closed and PCBs are seated. Without knowing which exact signals the PLC will send INDIA cannot add the I/O listener to orchestrator.py. | These input signals become the automation trigger layer. FCT_START replaces GUI button; PCB_IN_SLOT[1-4] lets FCT PC verify seats before powering PSU (safety); FIXTURE_CLOSED confirms mechanical lock before running Trace32 flash sequence. Together they make the test fully hands-off. | Without this list INDIA cannot implement the signal-listening loop. Manual operator start remains required — automation goal unmet. | HIGH | BANWA→INDIA
3 | Sec1 · Granularity | Per-Slot vs Per-Fixture PASS/FAIL | If PASS/FAIL is per-fixture (one combined signal after all 4 PCBs) the robot must wait until all 4 tests finish before releasing any PCB. If one PCB fails at t=10s but the others are still running until t=90s that PCB waits 80s unnecessarily. Per-slot signalling unlocks each PCB individually the moment its test completes. | Per-slot architecture directly reduces takt time. Robot arm or conveyor can pick from slot 1 at t=70s even while slots 3 and 4 are still running. This is the key to parallel throughput — the fixture is never idle waiting for the last PCB. | PLC fixture release logic and arm trajectory planning depend on this decision. A later change forces a complete PLC rewrite. | HIGH | BANWA decide
4 | Sec1 · Physical I/F | Physical Interface: USB-relay / PCIe / Ethernet | Python can control I/O through multiple hardware paths. Each requires a different driver library: USB-relay → usbrelay/hid library; PCIe I/O card → ctypes-based vendor SDK; Ethernet Modbus TCP → pymodbus. The choice also affects latency — USB-relay is ~10ms; Ethernet Modbus can be <5ms. Wrong library selection wastes dev time and may require hardware rework. | Once decided INDIA selects and installs the exact Python library writes the HardwareIOController class and can unit-test it on a bench before the full fixture arrives. This decouples I/O software from fixture availability compressing the schedule. | Hardware must be procured and arrive before any integration test. Long lead times on PCIe I/O cards can block the project. | HIGH | BANWA propose
5 | Sec1 · Voltage Level | Signal Voltage: 24V DC vs 5V DC | Industrial PLC I/O operates at 24V DC. Standard PC GPIO or USB-relay outputs are 5V DC. If connected directly the 24V signal destroys the PC's I/O hardware. An optocoupler isolation module or dedicated level-shifter board is required for 24V. This is a hardware-safety requirement not optional. | Knowing the voltage level allows INDIA to specify the exact isolation hardware (e.g. OMRON G3TB optocoupler relay board) in the BOM. If 5V is confirmed a simple USB-HID relay board suffices. This decision gates hardware procurement and determines whether a custom PCB adapter is needed. | Incorrect voltage selection risks permanent damage to test PC I/O ports. Must be resolved before any hardware purchase. | HIGH | BANWA
6 | Sec1 · Timing: START | FCT_START Pulse Width and Seat Hold Time | Python does not have hardware interrupts — it polls the I/O line in a software loop. If the PLC sends a 20ms pulse but Python polls every 50ms the pulse is missed and the test never starts. The rule is: Python poll interval must be ≤ half the minimum pulse width (Nyquist criterion for digital polling). | With the pulse width known INDIA sets the precise threading.Timer interval in the I/O listener and adds a debounce counter for the seat hold time. This prevents ghost triggers from PCB vibration during robot placement. Reliable start detection is foundational to zero-missed-cycle operation. | If pulse width is too short and Python loop too slow the system misses starts silently — operator sees nothing wrong but PCB is never tested. | HIGH | BANWA define
7 | Sec1 · Timing: DONE | FCT_DONE Hold Time | PLC scans its inputs in a fixed scan cycle (typically 5–20ms). If FCT_DONE is asserted for only 3ms but the PLC scan is 10ms the PLC may never see it. The FCT software must hold the signal asserted for at least 2× PLC scan cycle to guarantee detection with margin. | With the hold time number INDIA adds a time.sleep(hold_ms/1000) after asserting DONE signals. This is a 3-line code change but prevents intermittent missed-result bugs that are very hard to reproduce in integration testing. | Intermittent missed DONE signals cause the robot to stall waiting for a result that was already sent — production-line stoppage. | MED | BANWA define
8 | Sec1 · Handshake | Handshake Protocol | Without a handshake timing reliability depends on both sides having perfectly matched pulse widths and poll intervals — fragile in a real factory environment with electrical noise. A 3-step handshake (PLC sends START → FCT PC asserts ACK → PLC releases START → test begins) provides mutual confirmation that both sides are synchronised before the test starts. | Implementing a handshake eliminates the entire class of 'missed start' bugs. It also gives the PLC positive feedback that FCT PC is alive and responsive. The orchestrator.py state machine gains a WAITING_ACK state that cleanly models the automation flow making the code easier to maintain and debug. | Without handshake race conditions between PLC and Python can cause double-starts or skipped tests — impossible to diagnose remotely. | HIGH | Agree together
9 | Sec1 · ERROR Recovery | Error Recovery Sequence | When an FCT_ERROR occurs (e.g. Trace32 flash failure PSU overcurrent barcode unreadable) the robot must not continue placing new PCBs into the failed slot. The FCT software must hold FCT_ERROR asserted and the PLC must pause the robot arm assigned to that slot. An undefined recovery procedure means the robot keeps running and may damage PCBs or the fixture. | A defined recovery sequence becomes a state in the orchestrator state machine: ERROR_HOLD state asserts FCT_ERROR waits for a manual-clear signal (or auto-retry after N attempts) then transitions back to IDLE. This ensures production-safe operation and enables remote monitoring of error rates by slot. | Undefined error recovery is a production safety risk. A robot placing a new PCB into a failed slot can cause mechanical fixture damage. | HIGH | BANWA decide + INDIA implement
10 | Sec1 · READY Signal | FCT_READY Initialisation Signal | FCT software startup involves loading Trace32 connecting PSU over VISA and initialising PCAN. This takes 10–30 seconds. If PLC sends FCT_START during this period the test will fail immediately or crash. FCT_READY tells the PLC: 'all subsystems online safe to start.' Without it the PLC must blindly wait a fixed time after power-on. | Adding FCT_READY costs ~5 lines of Python: assert the signal at the end of the startup sequence in orchestrator.py. The PLC logic becomes: do not send FCT_START until FCT_READY is HIGH. This eliminates all startup-race failures and makes the system self-synchronising on power-on. | Without READY signal operators must manually wait a fixed time after power-on before starting production — introduces human error. | MED | Agree together
11 | Sec1 · Barcode Data Path | Barcode Scanner: Direct USB vs via PLC | Current NFC_Rev3.01 already reads barcodes via USB (scan_code field). If scanner connects directly to FCT PC INDIA's existing code works with zero changes. If the PLC reads barcode and passes it via a shared register or Ethernet protocol INDIA must add a PLC data reader — significant extra development. Direct USB is the lowest-risk path. | Confirming direct USB means INDIA keeps the existing barcode reader thread in orchestrator.py and simply adds slot-association logic. Via-PLC adds a PLCDataChannel class register mapping and error handling for PLC communication delays. The decision directly scopes INDIA's development effort by ±2 weeks. | If PLC-path is chosen without early confirmation INDIA may deliver software that expects USB barcodes but hardware is wired via PLC — complete rework required. | HIGH | Agree together
12 | Sec1 · Slot Identity | Barcode-to-Slot Mapping Scheme | With 4 slots running in parallel the CSV result file must correctly record which barcode belongs to which slot. If two PCBs are placed simultaneously the scan order may not match slot order. A slot-ID encoded in the FCT_START signal (e.g. 2-bit slot index) or a fixed scan-order convention is needed to prevent result misattribution — a traceability failure. | With the mapping scheme defined INDIA adds a slot_id parameter to the barcode reader call. Each parallel test thread receives its slot_id at start writes it to the result CSV and links it to the correct Trace32 session. Correct barcode traceability is often a customer audit requirement — this question directly enables compliance. | Wrong barcode-to-slot mapping means PASS results are recorded against the wrong PCB serial number — a quality system failure. | HIGH | Agree together
13 | Sec1 · Doc Ownership | I/O Spec Document Ownership | The I/O Signal Interface Specification is the contractual document between INDIA's FCT software and BANWA's PLC program. Both sides must implement exactly what is written. If ownership is unclear both sides may make independent changes that diverge discovered only during integration testing — the most expensive time to find disagreements. | Assigning INDIA as drafter means INDIA controls the signal names timing values and state machine which are natively part of the FCT software architecture. BANWA reviews and approves. This prevents a naming conflict (e.g. FCT PC calls signal 'SLOT_PASS_1' PLC calls it 'Y001') that would require joint debugging on-site in Thailand. | Without baselined I/F spec by 2026-07 BANWA cannot start PLC programming — direct schedule impact on system integration milestone. | MED | BANWA/INDIA
14 | Sec1 · 2 Fixture Types | Left/Right or NFC/NON-NFC Fixture Signal Sharing | The facility has two fixture types. If they share the same FCT_START/DONE signal lines one I/O hardware setup serves both — lower cost and simpler wiring. But FCT software must know which fixture type is active to load the correct test preset. If they have independent signal sets I/O hardware doubles but software is simpler. | Shared signals require INDIA to add a 'fixture_type' indicator signal or a parameter in the START trigger. Independent signals simplify software but require separate I/O channels relay boards and PLC outputs. This decision shapes the hardware BOM the Python HardwareIOController class design and the operator's workflow. | Ambiguity here causes INDIA to build for one model and discover at integration that the other fixture type uses different signals. | MED | BANWA define
SECTION 2 — FCT INSPECTION PROGRAM: 4-PCB PARALLEL ARCHITECTURE (INDIA solo)
15 | Sec2 · Architecture | 4-Slot Parallel: Multi-Process vs Multi-Thread | NFC_Rev3.01 tests one PCB sequentially. For 4-PCB parallel the code must run 4 independent test sequences simultaneously. Python's GIL prevents true CPU parallelism in threads for CPU-bound work. Multi-process (subprocess.Process) gives true isolation — if one slot crashes others continue. Multi-thread is lighter but requires thread-safe refactoring of shared objects (Trace32 PSU PCAN). | Choosing multi-process now guides the entire refactor of orchestrator.py. Each process gets its own Trace32Interface(port=N) PSU_Controller(visa_address=N) and PCAN_Interface(channel=N). A parent supervisor process monitors all 4 and reports to the PLC. This architecture is the blueprint for all subsequent Section 2 questions. | A wrong architecture choice discovered mid-development forces a complete rewrite. This is the highest-leverage early decision in the FCT program update. | HIGH | INDIA decide
16 | Sec2 · T32 Multi-Probe | Lauterbach: 4 Simultaneous Debug Connections | Trace32 is used to flash firmware to each PCB during FCT. Each connection requires one Lauterbach probe hardware unit and one software license. If 4-PCB parallel flashing is required 4 probes + 4 licenses cost ~€20000+. If sequential flash is acceptable (flash slots 1→2→3→4 in ~30s) one probe with multiplexed target connections suffices at a fraction of the cost. | Confirming sequential flash allows INDIA to design a single Trace32Interface with a slot selector that switches the JTAG mux between slots. This reduces hardware cost significantly while adding only ~30s to total cycle time. If production takt allows it sequential flash is strongly preferred. This answer gates the hardware procurement decision. | Procuring 4 probes without confirming the architecture could result in €15000+ unnecessary spend if sequential is acceptable. | HIGH | INDIA verify + Lauterbach
17 | Sec2 · T32 Python API | Trace32 Python API: 4 Simultaneous Instances | Current Functional/trace32.py uses global state: t32.dbg is a single connection object. In a multi-slot parallel design each slot's test thread needs its own Trace32Interface instance connected to a separate Trace32 intercom port (e.g. 20000 20001 20002 20003). If the library is not designed for multi-instance use all 4 slots share one connection and test results corrupt each other. | Verifying multi-instance capability of the Lauterbach Python API allows INDIA to write a clean Trace32Interface(slot_id port) class. Each process opens its own T32_Init() connection on a different port completely isolated. If the library does not support this INDIA must use subprocess calls to separate Trace32 instances — more complex but still achievable. | Unresolved API limitation can block the entire parallel flash architecture. Must be confirmed in lab before committing to multi-process design. | HIGH | INDIA verify
18 | Sec2 · PSU Per-Slot | PSU: Shared or 1-per-Slot | KIKUSUI PWR401L is rated 40V/1A. If each RH_i460 PCB draws 500mA during FCT one unit can barely power 2 PCBs with zero headroom. If peak current is 800mA during motor test one PSU cannot power even 2 PCBs simultaneously. Each PSU has a unique VISA address — 4 PSUs add 4 VISA connections and 4 PSU_Controller instances in Python. | Knowing the per-PCB current allows INDIA to calculate the supply budget and specify exactly N PSU units in the BOM. INDIA also designs the PSU_Controller pool: if 4 units each slot_id maps to a fixed VISA address. This hardware spec directly determines the cost of the test bench and cannot be changed after procurement. | Underspecified PSU causes supply voltage droop during parallel tests → incorrect electrical measurements → false FAILs → production line stop. | HIGH | INDIA verify HW spec
19 | Sec2 · PCAN Channels | PCAN Channels per PCB | PCAN-USB Pro FD provides 2 CAN FD channels per USB unit. If one RH_i460 PCB requires 1 CAN channel during FCT 4 PCBs need 4 channels = 2 PCAN-USB Pro FD units. If a PCB requires 2 channels 4 units are needed. Each unit has a unique channel identifier in the Python-CAN library. Wrong quantity means CAN tests fail on some slots. | With the CAN channel count confirmed INDIA writes a PCAN_Interface(slot_id) factory that maps slot 1→PCAN_USBBUS1 slot 2→PCAN_USBBUS2 etc. The procurement list is exact. No CAN channels are shared between slots ensuring test isolation. | Insufficient PCAN hardware means some slots have no CAN connection — those PCBs skip CAN tests silently and are shipped with untested CAN functionality. | HIGH | INDIA verify test spec
20 | Sec2 · PLIN Channels | PLIN Channels per PCB | LIN bus testing uses PLIN-USB hardware. If each PCB requires 1 LIN channel 4 units are needed for 4 parallel tests. Time-multiplexing 4 PCBs through 1 PLIN unit would add ~LIN_test_time × 4 to the cycle time per slot — defeating the parallel architecture goal. | Confirming PLIN channel count per PCB and feasibility of multiplexing allows INDIA to specify the exact PLIN hardware quantity and design the PLIN_Interface(slot_id) class. If 4 units are needed the BOM and USB port count on the test PC must accommodate them. | Missing PLIN units means LIN tests are skipped for some slots in parallel mode — functional test coverage gap. | HIGH | INDIA verify test spec
21 | Sec2 · Variant per Slot | Mixed NFC / NON-NFC Variants per Batch | Current code selects preset=2 (NFC) or preset=1 (NON-NFC) for the entire session. In production a batch might contain 3 NFC PCBs and 1 NON-NFC. If the variant is per-batch only the operator must run two separate batches — halving effective throughput. Per-slot variant selection lets each slot run its correct program independently. | Implementing per-slot variant selection means the GUI shows 4 dropdown selectors (one per slot) and passes variant_id to each parallel process at start. The Trace32 script called by each slot process differs accordingly. This unlocks mixed batches in production — a key flexibility requirement for manufacturing efficiency. | Forcing single-variant batches in a mixed-PCB production environment creates operator sorting overhead and reduces throughput. | MED | INDIA + production
22 | Sec2 · Start Trigger | Automation Start: PLC Signal vs GUI Button | This is the fundamental question that defines whether the system is 'automated' or 'semi-automated.' If the GUI button remains the trigger an operator must press it for every cycle — the robot automation is only material handling not full automation. If PLC FCT_START signal triggers the test zero operator interaction is needed during steady-state production. | Confirming PLC-signal trigger means INDIA removes the GUI Play button from the automation flow and replaces it with the I/O signal listener designed in Section 1 (Q1–Q8). The test cycle becomes: robot places PCB → PLC sends FCT_START → FCT tests → FCT sends PASS/FAIL → robot picks PCB → repeat. This is the definition of full automation. | Retaining GUI button as trigger defeats the entire automation objective. This question's answer is binary: full automation or not. | HIGH | INDIA + BANWA
23 | Sec2 · Sequence Changes | Test Steps Needing Modification for Auto Fixture | The CAPA test step uses DigitalSwitchController which simulates a capacitive touch press. In manual operation the test engineer presses a physical button on the PCB during this step. In an automated fixture there is no human hand — the fixture must include a pneumatic actuator or the CAPA step must use an electrical simulation. This is a hardware + software co-design issue. | By listing all steps that assume human interaction INDIA and BANWA can co-design the fixture to include actuators (pneumatic pins spring contacts) for each one. Steps that cannot be physically automated may need to be redesigned to use electrical simulation. Resolving this before fixture fabrication is critical — adding actuators after the fixture is built requires costly rework. | Unidentified manual-step requirements discovered during integration testing cause fixture redesign — worst-case 4–6 week delay. | HIGH | INDIA review + BANWA
24 | Sec2 · Test Duration | End-to-End Test Time per PCB (NFC_Rev3.01 NORMAL) | Takt time is the production target cycle time per unit. If each PCB takes 90s in the current NFC_Rev3.01 and the fixture holds 4 PCBs in parallel the theoretical cycle time is 90s for 4 PCBs = 22.5s per PCB. Management needs this number to confirm the automation meets the production target. Without it the business case for the automation investment cannot be validated. | Measuring the actual duration in NORMAL profile gives the baseline. INDIA can then calculate: 4-slot parallel takt = (test_time + robot_load_time) / 4. If takt exceeds production target INDIA can identify which test steps are longest and propose optimisations (e.g. reducing sg_measure from 3s to 2s reducing supply_on from 5s to 3s). This is the data management needs for ROI justification. | Without measured test time takt estimates are guesses. Management approval of the automation investment requires actual numbers. | HIGH | INDIA measure
25 | Sec2 · Power Cycle | Per-PCB PSU Power Cycle: Mandatory or Skippable | Between consecutive PCBs in one slot the current code performs supply_off → 2s wait → supply_on → 5s wait = 7s of dead time with no testing happening. If the PSU is already at the correct voltage and the PCB's microcontroller resets cleanly via Trace32 system reset this 7s may be unnecessary. Confirming this unlocks a takt improvement. | If confirmed skippable INDIA adds a 'warm_start' mode to PSU_Controller that skips power cycle when previous PCB's slot was a PASS. Saves 7s per PCB per slot. For 4 slots running across a full shift this is a meaningful throughput gain. If mandatory current code is already correct — confirming this prevents wasteful optimisation attempts. | Incorrectly skipping power cycle can leave residual charge on PCB capacitors → false pass on CAPA test or incorrect PSU current measurements. | MED | INDIA review
SECTION 3 — DATA LOGGING & RESULT FORMAT (INDIA solo)
26 | Sec3 · CSV Fields | Required CSV Fields per PCB | The production factory server has automated pick-up scripts that read the CSV result files. If the CSV column list does not match the server's expected schema (e.g. server expects 'serial_number' but INDIA writes 'barcode_id') the server script fails silently and the PCB traceability record is never created. This is a quality system failure that may not be discovered until an audit. | Getting the exact column list from the production team allows INDIA to hard-code the CSV writer in result_logger.py to produce exactly the right headers. A sample row with all 34 test items enumerated can be shared with the server team for validation before go-live. This single agreement prevents an entire class of post-deployment data integration bugs. | Mismatched CSV schema means zero traceability records are created in the production database — unacceptable for quality-certified manufacturing. | HIGH | INDIA + production
27 | Sec3 · File Naming | CSV File Naming Convention | Server-side automation often uses filename regex patterns to parse date barcode slot and result. If FCT software generates 'result_2026-06-11_slot1.csv' but the server expects 'YYYYMMDD_HHMMSS_ID_SlotN_PASS.csv' the file is either ignored or causes a parse error. Naming conventions are a low-effort agreement but a high-impact integration point. | Once the convention is agreed INDIA adds a single format string to result_logger.py: filename = f'{datetime.now():%Y%m%d_%H%M%S}_{barcode_id}_Slot{slot_no}_{result}.csv'. This is a 2-line code change. Agreeing it upfront avoids a file-naming change request after server scripts are already deployed. | Post-deployment filename changes require coordinated updates to server-side scripts — a change management overhead that slows production launch. | MED | INDIA + production
28 | Sec3 · MySQL | MySQL Logging: Required or CSV-Only | MySQL logging requires INDIA to install a database server write a db_logger.py module manage connection pooling for 4 parallel write threads handle duplicate key errors for retries and maintain a schema. This is ~2 days of additional development plus ongoing DBA responsibility. If CSV-only is sufficient (as the Condition sheet suggests) this scope is eliminated entirely. | A clear YES/NO decision from U-Shin management immediately either adds or removes 2 days from INDIA's schedule. If YES INDIA must ensure each parallel slot process uses a thread-safe database connection (e.g. SQLAlchemy connection pool). If NO the CSV writer is the only data output and the simpler architecture is confirmed. | Implementing MySQL without a decision from U-Shin creates unrequested scope and delays the core automation deliverables. | MED | U-Shin decision
29 | Sec3 · HTML Report | HTML Report: Per-PCB or 4-Slot Combined | Current NFC_Rev3.01 generates one HTML report per PCB. In a 4-slot parallel run 4 separate HTML files are generated. An operator checking results must open 4 files. A combined 4-slot batch report shows all 4 PCB results on one page — more useful at the test station. However it requires redesigning html_report_generator.py to accept a list of 4 result dicts and render a multi-slot layout. | If combined report is chosen INDIA refactors html_report_generator.py to accept batch_results[4] and generates a 4-panel HTML page. A per-PCB option is retained for reprint use. This improves operator usability and reduces the time to diagnose a batch failure. The decision scopes approximately 1 day of UI development. | Delivering per-PCB reports in a 4-slot context is functional but creates operator workflow friction — risk of manual error when checking results. | MED | INDIA decide
30 | Sec3 · Log Storage | Result File Storage: Local or Network Share | If results are written to a local PC path (e.g. C:\FCT_Results\) they are only accessible from the test PC itself. Production operators quality engineers or remote servers cannot access them without physically going to the test station. A network share (UNC path like \\factory-server\FCT_Results\) makes files immediately available to the server pickup script but requires stable network access and write permissions. | Confirming network share path allows INDIA to configure the result_logger.py output directory at installation time and add a network-connectivity check to the FCT startup sequence (alert if share is unreachable). This makes the data pipeline end-to-end: test completes → file written → server picks up → database updated — fully automated traceability. | Local-only storage creates a manual data transfer step (USB copy FTP) — a manual operation in an otherwise fully automated system. | MED | Production team
SECTION 4 — SCHEDULE & DELIVERABLES (INDIA planning)
31 | Sec4 · I/F Spec Date | I/O Interface Spec Finalisation Date | BANWA's PLC program for robot and fixture control cannot begin until the I/O Signal Interface Specification is agreed and signed off. The PLC program is on the critical path for the '26_7 schedule milestone. INDIA's I/F design is estimated at 2–3 weeks from '26_6. If INDIA starts now the spec can be ready by end-June 2026 giving BANWA a full month to begin PLC programming before the July milestone. | Setting a hard date creates accountability: INDIA commits to delivering the spec draft by Date X; BANWA commits to review feedback by Date X+5 days; sign-off by Date X+10. This schedule agreement is the single most important coordination point between the two teams. Without it BANWA waits indefinitely and the July milestone slips. | Every week of delay to the I/F spec directly delays BANWA's PLC program by one week — a 1:1 schedule impact on the integration milestone. | HIGH | INDIA + BANWA
32 | Sec4 · FCT Review Scope | Scope of '2 Months FCT Review' | The project schedule allocates '2 months' for FCT review. But this scope is ambiguous: does it mean (a) code update only done remotely (b) code update + desk testing on bench hardware or (c) code update + on-site integration with the new fixture at the Thailand factory? Option (c) would require travel fixture availability and full system integration — likely more than 2 months. Scope definition is essential before INDIA commits to the timeline. | A clear scope definition allows INDIA to create a Work Breakdown Structure: Week 1-4 code update Week 5-6 bench test with bench hardware Week 7-8 on-site integration support (if included). If on-site integration is out of scope INDIA delivers tested code and BANWA leads integration with remote INDIA support. This directly determines whether the 2-month estimate is achievable. | An underscoped '2 months' estimate discovered at the 6-week mark causes project delay and budget overrun — must be resolved before work starts. | HIGH | INDIA + HMM-HQ
33 | Sec4 · Integration Test | Integration Test: On-Site vs Remote | End-to-end integration testing requires both INDIA's software and BANWA's hardware operating simultaneously. If INDIA is remote every I/F timing issue requires a screen-share debug session with BANWA. On-site debugging resolves issues in hours that take days remotely due to time zones and communication overhead. This is especially critical for the FCT_START handshake timing and signal voltage issues from Section 1. | Agreeing on-site support for integration testing protects the schedule. If INDIA engineers are on-site in Thailand for 1-2 weeks during integration the estimated resolution time for timing bugs wiring issues and software-hardware mismatches drops dramatically. Combined with the handshake and voltage questions from Section 1 on-site presence is the single best risk mitigation for the integration phase. | Purely remote integration increases debugging time by ~3x for hardware/software interface issues — direct risk to the '26_7 schedule. | MED | BANWA + INDIA
34 | Sec4 · Acceptance Criteria | Acceptance Criteria for FCT Software Delivery | Without defined acceptance criteria the FCT software delivery has no formal closure condition. INDIA believes it is done; HMM-HQ or U-Shin finds a gap. Disputes over whether the software 'passed' delay production launch. Defined criteria — e.g. zero false-PASS rate over 100 consecutive cycles ≥99% barcode traceability on 500 PCBs test time within takt — create an objective pass/fail gate. | INDIA uses the acceptance criteria to design the validation test protocol: run N cycles measure false-PASS rate verify CSV files on server measure takt time against target. When all criteria are met INDIA signs off. This protects both INDIA (against scope creep) and U-Shin (against software that passes superficially but fails in production). It is the formal definition of 'done.' | Without acceptance criteria project closure becomes a negotiation not a measurement — leading to prolonged warranty disputes and unplanned rework. | MED | U-Shin / HMM-HQ
COLOUR LEGEND: Green (col D) = WHY — technical reason this question must be answered ¦ Yellow (col E) = HOW — contribution to full automation ¦ Red priority = HIGH (schedule/safety blocker) ¦ Orange priority = MED (important but not blocking)

## Component_Diagram
FULL AUTOMATION FIXTURE — HIGH-LEVEL COMPONENT DIAGRAM (RH_i460 FCT ¦ 4-Slot Parallel ¦ India FCT SW + BANWA PLC/Robot)
The SVG diagram file 'Full_Automation_Component_Diagram.svg' is in the same folder. Open it in Chrome/Edge for the full interactive view. ¦ HTML viewer: Full_Automation_Component_Diagram.html