## BOM Preparation Roadmap
SmartBU Automation Fixture – BOM Preparation Roadmap
Step | Activity | Details / Action Required | Information Source | Owner | Status
▶ UNDERSTAND THE DUT
1.1 | Review PCB Assembly Drawings | Open ASSY_TOP.pdf and ASSY_BOTTOM.pdf for all 4 variants: • NFC RH – 132309000037J_ASSY_TOP.pdf • NFC LH – 132309000039K_ASSY_TOP.pdf • nonNFC RH – 132309000037J_ASSY_TOP.pdf • nonNFC LH – 132309000039K_ASSY_TOP.pdf Identify: PCB outline dimensions, connector positions, test pad locations | Gerber_Data\...\132309000037\*.pdf | Engineer | PENDING
1.2 | Extract DUT Component BOM | Open the BOM Excel files for each variant: • 132302500036O_BOM.xlsx (NFC RH) • 132302500038P_BOM.xlsx (NFC LH) • 132302500040N_BOM.xlsx (nonNFC RH) • 132302500041N_BOM.xlsx (nonNFC LH) Filter for: connectors (J*), test points (TP*), large mechanical parts | Gerber_Data\...\132302500036\*.xlsx | Engineer | PENDING
1.3 | Read PCB Description Documents | Open the 090 description_*.doc files – these contain functional block descriptions and signal lists per connector: • 090 description_C652-10.doc (RH board) • 090 description_C654-11.doc (LH board) → Map each connector pin to its signal name (CAN, LIN, Motor, JTAG, GND, VCC…) | Gerber_Data\...\090 description_*.doc | Engineer | PENDING
1.4 | Check PCB Layer Stackup | Open Layer_Stackup.xlsx in each variant folder. Extract: total PCB thickness. → This value determines minimum pogo pin working stroke. | Gerber_Data\...\Layer_Stackup.xlsx | Engineer | PENDING
▶ DEFINE TEST CONTACT STRATEGY
2.1 | List all Test Points & Signals to Contact | From Phase 1 data, create a consolidated table: Ref Des ¦ Signal ¦ Connector/TP ¦ Voltage ¦ Current ¦ Notes Expected signals: VCC (battery), GND, CAN-H, CAN-L, LIN, Motor A/B/C, Hall sensors, JTAG (SWDIO/SWDCLK/RESET/VCC_TARGET), NFC antenna (LH/NFC only) | DUT BOM + Description docs + Test Procedures (LH/RH TP.pdf) | Engineer | PENDING
2.2 | Decide Contact Method per Signal Group | For each signal group decide: • HIGH CURRENT (motor, battery): pogo pin with large tip / screw terminal • SIGNAL (CAN, LIN, JTAG): standard 1mm or 1.27mm pogo • NFC antenna: loop coil or flat copper trace coupling Document the contact method for each group. | Engineering judgement + existing RR_VT fixture reference | Engineer | PENDING
2.3 | Determine Pogo Pin Count | Sum all signals requiring automated contact. Add 20% spare positions for future signals. → This sets the size of the pogo pin carrier PCB. | Signal table from step 2.1 | Engineer | PENDING
▶ MECHANICAL DESIGN INPUTS
3.1 | PCB Outer Dimensions & Fiducials | From assembly PDFs: extract PCB width, height, corner radius. Identify fiducial marks or tooling holes used for alignment. → Used to design alignment pins / guide posts in the fixture. | ASSY_TOP.pdf / Gerber outline layer | Engineer | PENDING
3.2 | Choose Actuation Method | Select ONE: A) Pneumatic: cylinder + solenoid valve + FRL unit + compressor B) Electric linear actuator: motor driver + ball screw C) Manual lever with sensor feedback (lowest cost) → Decision drives 30–40% of BOM items. | Project constraints (cost, cycle time, space) | Project Lead | DECISION NEEDED
3.3 | Calculate Actuation Force & Stroke | Force = (number of pogo pins) × (pogo contact force per pin in grams) Typical pogo: 50–150g each. Example: 20 pins × 100g = 2 kg → ~20 N min. Stroke = PCB thickness + pogo overtravel (typically 1–2 mm) + clearance. → Use this to select cylinder bore or actuator model. | Pogo pin datasheets + Layer_Stackup.xlsx | Engineer | PENDING
3.4 | Design Pogo Pin Carrier PCB / Block | Define: • Grid pitch matching DUT test pad pitch • PCB size and mounting holes • Material (FR4 / PEEK for high-temp applications) Reference: RR_VT fixture uses Harwin test pins on custom carrier board. | Signal table + PCB drawing | PCB Designer | PENDING
▶ ELECTRICAL / INSTRUMENTATION
4.1 | Confirm CAN Interface Hardware | Verify the CAN interface already in use (likely PEAK PCAN-USB or Vector). Confirm part number and add to BOM with quantity. Check if a second channel is needed for LH + RH simultaneous testing. | Existing lab setup / T32_JLINK Config folder | Engineer | CONFIRM
4.2 | Confirm LIN Interface Hardware | Verify LIN master interface (USB-LIN adapter or in-built on CAN tool). Add part number and quantity to BOM. | Existing lab setup | Engineer | CONFIRM
4.3 | Confirm JTAG Debugger | Already documented in T32_JLINK setup. Confirm: Lauterbach TRACE32 or SEGGER J-Link? Check if the existing debugger supports automated (headless) use. Add license dongle if required. | T32_JLINK\SmartBU\Debugger_hw.jpg + How_To_Debugg.xlsx | Engineer | CONFIRM
4.4 | Specify Programmable Power Supply | Required specs: • Output voltage range: covers DUT operating voltage (check test procedure) • Current rating: motor stall current × 1.5 safety factor • Remote control interface: USB / LAN / GPIB Suggested: Keysight E36xx or Rohde & Schwarz NGE100 series. | LH_i460_NON_NFC_TP.pdf / RH_i460_NFC_TP.pdf | Engineer | PENDING
4.5 | Relay / Signal Switching Board | For signals not directly in pogo contact (bus enables, load switches): • Determine number of switched channels • Choose relay board (USB HID relay board, or PLC digital output) • Confirm voltage and current rating per channel | Signal table from step 2.1 | Engineer | PENDING
4.6 | Barcode / Datamatrix Reader | Already integrated in the project (Barcode_Reader folder). Confirm: reader model, cable interface (USB/RS232), mounting bracket. Add to BOM. | Continous_Developement\Nfc_Version\Barcode_Reader | Engineer | CONFIRM
▶ SAFETY & SENSORS
5.1 | DUT Presence Sensor | Sensor to confirm PCB is correctly loaded before power/actuation. Options: optical fork sensor, inductive proximity, mechanical micro-switch. Define: mounting position, cable length, output type (NPN/PNP/digital). | Fixture mechanical drawing | Engineer | PENDING
5.2 | Actuator Position Sensors | Two sensors needed: OPEN position + CLOSED (contacted) position. Type: magnetic reed switch or inductive sensor integrated in actuator. Used by software to confirm safe state before/after actuation. | Actuator datasheet | Engineer | PENDING
5.3 | Emergency Stop Button | Required if fixture has powered actuation. Standard IEC 60947-5-5 mushroom head E-stop, panel mount. Add to BOM with cable and din-rail mount relay module. | Safety requirement | Engineer | PENDING
▶ CABLING & WIRING
6.1 | Create Wiring Diagram | Draw a wiring diagram from: Pogo carrier → breakout board → instruments (CAN, LIN, PSU, JTAG, relays) Define: signal names, wire gauge, shielding (CAN/LIN = twisted pair shielded), connector types at each end. | Signal table + instrument specs | Engineer | PENDING
6.2 | List All Connectors & Cables | For each harness segment list: • Connector type & part number (both ends) • Wire gauge (AWG) • Shielded or unshielded • Length Reference: RR_VT fixture uses DB25 for multi-signal harness. | Wiring diagram from 6.1 | Engineer | PENDING
▶ ASSEMBLE FINAL BOM
7.1 | Consolidate All BOM Sections | Combine into one BOM document with columns: Item# ¦ Category ¦ Description ¦ Manufacturer ¦ Part No. ¦ Qty ¦ Unit ¦ Unit Cost ¦ Total Cost ¦ Source ¦ Status Categories: Mechanical, Actuation, Pogo/Contact, Electrical, Instruments, Cables, Safety | All previous phases | Engineer | PENDING
7.2 | Review and Validate BOM | Cross-check BOM against: • Test procedure (all signals covered?) • Existing BOM_SmartBU_Automation.xlsx (avoid duplicates) • RR_VT_PCB_BOM_Rev2.0.xlsx (reference fixture for similar items) Get sign-off from project lead. | All previous sources | Project Lead | PENDING
7.3 | Get Quotations for New Items | For all items marked PENDING procurement: • Request quotes from: Harwin, Farnell, RS Components, Misumi • For custom mechanical parts: get quotes from machine shop • For custom PCB (pogo carrier): get quotes from PCB manufacturer | Final BOM | Procurement | PENDING

## Have vs Need
SmartBU Automation Fixture – What We Have vs What We Need
# | Category | Item / Document | Status | Details / Gap | Action Required | Priority
── DOCUMENTS ──
1 | Documents | Manual Fixture Setup Photos (Hw_Setups/*.png) | HAVE ✓ | 6 photos: fixture assembly, sensor PCB connections, motor connections, debugger wiring | None – already documented | —
2 | Documents | Test Procedures (LH + RH) LH_i460_NON_NFC_TP.pdf RH_i460_NFC_TP.pdf | HAVE ✓ | Full test procedures for both hand sides available | Extract: voltage/current specs, test sequence, signal list | HIGH
3 | Documents | How_To_Debugg.xlsx | HAVE ✓ | Debugging procedure documented | None | —
4 | Documents | PCB Gerber data – all 4 variants (Gerber_Data/XNF I460 _20251208/) | HAVE ✓ | 4 PCB variants: NFC LH/RH, nonNFC LH/RH Assembly drawings, BOM, drill files, ODB++ included | Open ASSY_TOP.pdf to extract connector positions and test pad coordinates | HIGH
5 | Documents | DUT Component BOMs (132302500036O_BOM.xlsx etc.) | HAVE ✓ | 4 BOM files – one per PCB variant | Open and filter for connectors (J*) and test points (TP*) | HIGH
6 | Documents | PCB Description Documents (090 description_C652-10.doc etc.) | HAVE ✓ | Functional description per board variant | Read to extract signal mapping per connector pin | HIGH
7 | Documents | PCB Layer Stackup (Layer_Stackup.xlsx) | HAVE ✓ | Available in each variant folder | Extract total PCB thickness for pogo pin stroke calculation | MEDIUM
8 | Documents | Automation Scripts (T32_JLINK/AutomationScripts/) | HAVE ✓ | Existing test automation scripts available | Review to confirm which hardware interfaces are already used | MEDIUM
9 | Documents | Reference Fixture BOM (RR_VT_PCB_BOM_Rev2.0.xlsx) | HAVE ✓ | Another fixture BOM available as reference for similar items | Use as reference for pogo pin, connector, and PCB design | MEDIUM
10 | Documents | Signal-to-Test-Point Mapping Table | NEED ✗ | No consolidated table exists yet mapping each DUT signal to its contact point | Create by cross-referencing: 090 description doc + DUT BOM + test procedures | CRITICAL
11 | Documents | Wiring Diagram (Fixture → Instruments) | NEED ✗ | No wiring diagram for automation fixture exists yet | Create after completing signal mapping (step 10) | HIGH
── MECHANICAL ──
12 | Mechanical | PCB Outline Drawing / Dimensions | PARTIAL ~ | Available in Gerber assembly PDFs but not yet extracted as a standalone dimension drawing | Open ASSY_TOP.pdf and extract: width, height, tooling holes, fiducials | HIGH
13 | Mechanical | Fixture Base Plate | NEED ✗ | No base plate drawing or part defined yet | Define: material (aluminium), dimensions, mounting pattern for instruments and actuator | HIGH
14 | Mechanical | Alignment Pins / Guide Posts | NEED ✗ | Manual fixture uses the PCB edge – automation requires precision guide posts | Derive from PCB tooling hole coordinates in drill file | HIGH
15 | Mechanical | PCB Carrier / Nest (DUT holder) | NEED ✗ | No automated PCB nest designed yet | Design custom nest matching PCB outline + actuation direction | HIGH
16 | Mechanical | Pogo Pin Carrier PCB or Block | NEED ✗ | No pogo carrier designed yet Reference: RR_VT uses Harwin pins on custom PCB | Design after signal mapping is complete (step 10) | HIGH
17 | Mechanical | Actuator (Pneumatic or Electric) | NEED ✗ | Decision not made yet – pneumatic cylinder or electric linear actuator | Make actuation method decision first, then specify model, stroke, bore/force | CRITICAL
18 | Mechanical | Mounting Hardware (screws, standoffs, DIN rail) | NEED ✗ | Standard hardware – not yet listed | Add after base plate and PCB carrier are defined | LOW
── ELECTRICAL / INSTRUMENTS ──
19 | Instruments | JTAG Debugger (T32 or J-Link) | PARTIAL ~ | Debugger documented in T32_JLINK setup, hardware photo exists | Confirm: exact model number, cable type, add to BOM with quantity | HIGH
20 | Instruments | CAN Bus Interface (PEAK / Vector) | PARTIAL ~ | Used in existing scripts but part number not confirmed | Confirm model (e.g., PCAN-USB) and add to BOM | HIGH
21 | Instruments | LIN Bus Interface | PARTIAL ~ | Referenced in automation scripts, hardware not yet specified in BOM | Confirm model and add to BOM | HIGH
22 | Instruments | Programmable Power Supply | NEED ✗ | No PSU specified yet Must support remote control (USB/LAN/GPIB) | Extract DUT voltage/current from test procedure, then select PSU model | HIGH
23 | Instruments | Relay / Signal Switching Board | NEED ✗ | No relay board specified yet | After signal mapping: count switched channels, choose relay board | MEDIUM
24 | Instruments | Barcode / Datamatrix Reader | PARTIAL ~ | Already integrated in software (Barcode_Reader folder) but hardware BOM entry missing | Confirm reader model, add to BOM with mounting bracket | MEDIUM
── POGO PINS / CONTACT ──
25 | Contact | Pogo Pin Part Number and Spec | NEED ✗ | Not defined yet Reference: RR_VT uses Harwin-type test pins (A700000008880531, A700000008880563) | After signal mapping: specify per contact type (signal, power, HV) Check Harwin pins already in RR_VT BOM | HIGH
26 | Contact | Total Pogo Pin Count | NEED ✗ | Cannot be determined until signal-to-pad mapping table is complete | Complete step 10, then count all pins + add 20% spare | HIGH
27 | Contact | Pogo Pin Carrier Board (Gerber) | NEED ✗ | No design exists yet | Design after pogo count and grid pitch are defined | MEDIUM
── SAFETY ──
28 | Safety | DUT Presence Sensor | NEED ✗ | No presence sensor specified | Select: optical fork, inductive proximity, or micro-switch Add to BOM | MEDIUM
29 | Safety | Actuator Position Sensors (open/closed) | NEED ✗ | Required for automated control loop Typically 2 sensors per actuator | Select based on actuator type chosen in step 3.2 (item 17) | MEDIUM
30 | Safety | Emergency Stop Button | NEED ✗ | Required if powered actuation is used | Standard IEC 60947-5-5 mushroom head E-stop Add to BOM | MEDIUM
── CABLING / WIRING ──
31 | Cabling | Signal Harness: Pogo Carrier → Instruments | NEED ✗ | No harness designed yet | Create after wiring diagram is done (item 11) | MEDIUM
32 | Cabling | CAN Bus Cable (twisted pair shielded) | NEED ✗ | Not yet specified | Specify wire gauge, length, connector types at both ends | MEDIUM
33 | Cabling | LIN Bus Cable | NEED ✗ | Not yet specified | Specify wire gauge, length, connector types | MEDIUM
34 | Cabling | Power Cable (PSU → Pogo Carrier) | NEED ✗ | Not yet specified Current rating depends on DUT motor load | Extract max current from test procedure before specifying wire gauge | MEDIUM
35 | Cabling | JTAG Ribbon Cable | PARTIAL ~ | Existing manual connection uses ribbon cable BOM entry not confirmed | Confirm part number from existing setup, add to BOM | LOW
── SOFTWARE ──
36 | Software | Automation Test Scripts (T32_JLINK/AutomationScripts/) | HAVE ✓ | Existing scripts available for NFC/nonNFC LH and RH | Review if scripts need updates to support automated fixture I/O (relay, PSU, sensor) | MEDIUM
37 | Software | Fixture Controller Interface (actuator + relay + sensor control) | NEED ✗ | No software exists yet for controlling the physical automation fixture hardware | Develop after hardware (actuator, relay, sensors) is defined | HIGH
38 | Software | MySQL Integration for Results Logging | HAVE ✓ | MySQL integration exists in project (MySQL/ folders) | Verify it covers automation fixture results or needs extension | LOW

## Legend
Legend / Key
STATUS
✓ | HAVE | Item or document already available – no procurement needed
~ | PARTIAL | Item partially available – confirm details or add to BOM
✗ | NEED | Item missing – must be sourced, designed, or created
STEP STATUS
| PENDING | Work not yet started
| CONFIRM | Item likely exists – verify part number and add to BOM
| DECISION NEEDED | A design/procurement decision must be made before proceeding
| DONE | Step completed
PRIORITY
| CRITICAL | Blocks multiple downstream tasks – address first
| HIGH | Required before BOM can be submitted
| MEDIUM | Required before fixture can be built
| LOW | Can be finalised later in the project