## Slide 1
Project Datewise Status
Presentation summary prepared from the status screenshot
11
Projects / tracks
04 Jun
Latest feedback date
06 Jun
JA00 SWIT target
23 Jun
JLR_NFC release-test hold
Focus: testing milestones, feedback closure, integration readiness, hardware progress, and open planning items.
Project datewise status | 04 June 2026 | Slide 1

## Slide 2
Executive Summary
High-level message for management review
Near-term testing
JA00 SWIT completes on 6 June and SWRT starts on 8 June.
Feedback status
Steering Switch feedback is closed, with new feedback received on 4 June.
Design and compliance
JLR_NFC SWDD, ASPICE readiness, and traceability activities are progressing.
Integration
E-Mirror and pinching detection are moving toward single-application vehicle execution.
Hardware
RRVT hardware and SmartBU fixture/PCB tests are active, with one PCB heating issue observed.
Project datewise status | 04 June 2026 | Slide 2

## Slide 3
Testing and Requirements Tracks
Detailed status items grouped from the screenshot
JA00
In Progress
SWIT testing will be completed on 6th June.
SWRT testing will start on 8th June.
MBSE
In Progress
Team is creating EA models for PLG functional requirements.
DigiKey
In Progress
Positioning algorithm improving.
Updating PC application using Python script.
Steering Switch
Completed / New Feedback
All feedback is completed. New feedback received on 4th June.
JLR_NFC
Planned
System architecture and system requirement analysis with SW test-case traceability is maintained.
No release test till 23rd June.
SW detailed design review in enterprise architecture.
ASPICE assessment is planned for mid-August.
SW unit test cases improved based on updated SWDD.
Project datewise status | 04 June 2026 | Slide 3

## Slide 4
Development and Integration Tracks
Detailed status items grouped from the screenshot
BMW Dev
Mixed
Jashan is improving NFC detection on RR handle and fixing no-detect issue at high temperature PR.
Yash fixed MISRA fixes for StoOpsum and CapaAppMunich; merge pending for CapaAppMunich.
VoltM and TempM detailed design review feedback is pending.
RRVT
In Progress
Hardware activities ongoing.
PCB design for RRVT.
RRVT card connections.
Needle bed work with mechanical team for RR needle bed.
Seamless Entry
Feedback Awaited
New exit intent detection in Pinching_detection_1_2 feedback is present.
Detection and 'Hand on thigh' detection are not functioning properly.
Gurpratap made code changes, prepared a test video, and feedback is awaited.
E-Mirror
In Progress
Mode switching between Gesture and Rearward Confirmation feedback is OK.
Pinching detection and e-mirror application are being integrated into a single application to run on the real vehicle.
Project datewise status | 04 June 2026 | Slide 4

## Slide 5
Hardware, Validation, and Team Planning
Detailed status items grouped from the screenshot
SmartBU
In Progress
Both fixture NFC Right side and NON-NFC Left side tested on Rev3.01.
19 PCB2 tested; only one PCB gets hot in EOS test.
Tested 100pF and 20pF capacitors using automatic switch test; reports and videos captured for evidence.
Plan to test PCB1 with fixtures today.
Welfare
Planning
Planning for another cricket match on Saturday.
Get-together party needs planning after 6 months.
Reward engineers who consistently show more effort and strong timing.
Project datewise status | 04 June 2026 | Slide 5

## Slide 6
Next Actions
Suggested talking points and follow-ups
JA00: Track SWIT closure by 6 June and prepare SWRT start readiness for 8 June.
JLR_NFC: Confirm release-test hold till 23 June and ASPICE preparation timeline.
BMW Dev: Close CapaAppMunich merge and complete VoltM/TempM detailed-design feedback.
Seamless Entry: Review test video feedback for exit-intent and hand-on-thigh detection.
SmartBU: Investigate the PCB heating observation and complete PCB1 fixture testing.
Welfare: Finalize cricket match and get-together planning owners/date.
Project datewise status | 04 June 2026 | Slide 6

## Slide 7
Presenter Notes
Use this slide as backup or remove before presenting
Source and Assumptions
The deck is prepared from the visible text in the screenshot shared by the user.
Items partly cut off in the screenshot were not expanded beyond what was readable.
Recommended presentation flow: summary, testing tracks, development/integration tracks, hardware/planning, next actions.
Project datewise status | 04 June 2026 | Slide 7