## Summary
Topic | Plan Summary
Objective | Replace CANoe in the SmartBU EOL bench with a Python-based CAN/LIN communication layer while keeping debugger/programmer control separate.
Alternatives | Option A: Kvaser Hybrid 2xCAN/LIN. Option B: PEAK PCAN-USB Pro FD. Both plans assume J-Link as the lower-cost debugger/programmer replacement for Trace32 in a later work package.
Common Scope | Bench communication, CAN/LIN stimulation and capture, barcode-based traceability, test result logging, Excel and CSV reports, GUI integration, pilot validation, and release package for production rollout.
Recommendation | Run the common phase 0 and phase 1 tasks once, then execute either the Kvaser-specific or PEAK-specific integration stream. Final selection should be based on pilot KPI results, implementation effort, and 3-year station TCO.

## Kvaser Plan
Phase | Workstream | Activity | Deliverable | Owner | Duration | Dependency | Risk / Note
P0 | Requirements | Freeze EOL scope, DUT variants, CAN IDs, LIN PIDs, barcode rules, report content, and pilot KPIs. | Approved requirement baseline | System Lead | 3 days | Stakeholder workshop | Changing scope later will delay both hardware alternatives.
P1 | Procurement | Procure Kvaser Hybrid 2xCAN/LIN, cables, terminal adapters, and one spare unit. | Bench hardware kit | Buyer | 1 week | Approved BOM | Lead time and regional distributor availability must be checked early.
P1 | Environment | Install Kvaser CANlib and LINlib drivers, validate device enumeration on the production PC image, and define Python package baseline. | Reference station image | Software Eng. | 3 days | Hardware arrival | Driver version pinning is required for repeatable station rollout.
P2 | Architecture | Define vendor-neutral bus adapter interface and Kvaser-specific implementation for CAN open/close, LIN open/close, Tx/Rx, timeout, logging, and health check. | Adapter design spec | Software Lead | 4 days | Requirement baseline | Avoid hard-coding Kvaser APIs in GUI code.
P2 | Implementation | Implement Kvaser CAN backend, LIN backend, and optional UDS transport wrapper for required production services. | Working Kvaser communication module | Software Eng. | 2 weeks | Architecture approval | LIN API behavior and scheduling model should be proven early with real DUT traffic.
P3 | GUI Integration | Add hardware selection, connection status, start/stop flow, barcode gating, and test result integration into the existing SmartBU GUI and automation runner. | Integrated GUI build | Software Eng. | 1 week | Kvaser backend ready | Keep current report and barcode logic unchanged except metadata wiring.
P3 | Test Logic | Refactor CAN/LIN verdicts from Trace32-local loopback assumptions to real external-bus validation with Kvaser Tx/Rx and timing checks. | Updated test sequences | Validation Eng. | 1 week | Kvaser backend ready | This is the key functional delta versus the current codebase.
P4 | Bench Validation | Execute smoke tests, 50-cycle soak test, communication timeout test, cable disconnect recovery, and barcode/report traceability checks. | Validation report | Validation Eng. | 1 week | Integrated GUI build | Use same DUT lot for both alternatives if A/B comparison is required.
P5 | Pilot | Pilot on one station with agreed sample size, compare yield, cycle time, false fail rate, and recovery time against baseline. | Pilot KPI dashboard | Project Lead | 1-2 weeks | Validation report | Decision gate for production approval.
P6 | Release | Freeze versions, prepare operator SOP, recovery guide, maintenance checklist, and station rollout package. | Production release bundle | System Lead | 3 days | Pilot sign-off | Must include exact Kvaser driver versions and USB identification steps.

## PEAK Plan
Phase | Workstream | Activity | Deliverable | Owner | Duration | Dependency | Risk / Note
P0 | Requirements | Freeze EOL scope, DUT variants, CAN IDs, LIN PIDs, barcode rules, report content, and pilot KPIs. | Approved requirement baseline | System Lead | 3 days | Stakeholder workshop | Common task shared with Kvaser plan.
P1 | Procurement | Procure PEAK PCAN-USB Pro FD, CAN/LIN connection cables, terminal adapters, and one spare unit. | Bench hardware kit | Buyer | 1 week | Approved BOM | Confirm exact adapter cable set for simultaneous CAN and LIN bench wiring.
P1 | Environment | Install PCAN-Basic, PLIN API, monitor tools, validate enumeration on the production PC image, and define Python package baseline. | Reference station image | Software Eng. | 3 days | Hardware arrival | Windows driver and API package versions should be frozen after pilot.
P2 | Architecture | Define vendor-neutral bus adapter interface and PEAK-specific implementation for CAN open/close, LIN open/close, Tx/Rx, timeout, logging, and health check. | Adapter design spec | Software Lead | 4 days | Requirement baseline | Do not expose PCAN or PLIN details directly in GUI code.
P2 | Implementation | Implement PEAK CAN backend, LIN backend, and optional UDS transport wrapper for required production services. | Working PEAK communication module | Software Eng. | 2 weeks | Architecture approval | Validate LIN mode and physical wiring with DUT before full GUI integration.
P3 | GUI Integration | Add hardware selection, connection status, start/stop flow, barcode gating, and test result integration into the existing SmartBU GUI and automation runner. | Integrated GUI build | Software Eng. | 1 week | PEAK backend ready | This task is largely shared with the Kvaser path.
P3 | Test Logic | Refactor CAN/LIN verdicts from Trace32-local loopback assumptions to real external-bus validation with PEAK Tx/Rx and timing checks. | Updated test sequences | Validation Eng. | 1 week | PEAK backend ready | Bus verdict logic must be identical across both hardware alternatives.
P4 | Bench Validation | Execute smoke tests, 50-cycle soak test, communication timeout test, cable disconnect recovery, and barcode/report traceability checks. | Validation report | Validation Eng. | 1 week | Integrated GUI build | Use same DUT lot for fair comparison if A/B decision is still open.
P5 | Pilot | Pilot on one station with agreed sample size, compare yield, cycle time, false fail rate, and recovery time against baseline. | Pilot KPI dashboard | Project Lead | 1-2 weeks | Validation report | Decision gate for production approval.
P6 | Release | Freeze versions, prepare operator SOP, recovery guide, maintenance checklist, and station rollout package. | Production release bundle | System Lead | 3 days | Pilot sign-off | Must include exact PEAK driver/API package versions and adapter cable map.