## System Overview (hidden)
System Overview — Conveyor-Fed Automatic PCB Test Station
┌─────────────────────────────────────────────────────────────────────────────────────────────────┐
│ CONVEYOR-FED AUTOMATIC PCB TEST STATION — SYSTEM OVERVIEW │
└─────────────────────────────────────────────────────────────────────────────────────────────────┘
[UPSTREAM CONVEYOR] ──► [ENTRY STOPPER ↑] ──► [BARCODE SCANNER] ──► [PRESS STATION] ──► [EXIT]
│
┌──────────┴──────────┐
│ PNEUMATIC PRESS │
│ (Top plate + pogo │
│ pin carrier down) │
│ + Connector plug-in │
└──────────┬──────────┘
│
┌──────────┴──────────┐
│ TEST INSTRUMENTS │
│ • KIKUSUI PWR401L │
│ • Lauterbach Trace32│
│ • PCAN-USB (CAN) │
│ • PLIN-USB (LIN) │
└──────────┬──────────┘
│
┌──────────┴──────────┐
│ TEST PC │
│ orchestrator.py │
│ gui_main.py │
│ MySQL logging │
│ HTML report │
└──────────┬──────────┘
│
PASS ◄───────────────┼───────────────► FAIL
│ │
[EXIT CONVEYOR] [REJECT TRAY]

## Flow Diagram (hidden)
XNF FCT AUTOMATION — FULL SYSTEM DESIGN & FLOW DIAGRAM
Product: RH_i460 NFC/NON-NFC ¦ Config: 2 Fixtures × 4 Slots = 8 PCBs/cycle ¦ Base FCT: NFC_Rev3.01 ¦ Date: 2026-06-09
① MATERIAL INPUT
[5 empty] | INPUT TRAY STACK MAGAZINE |  |  |  | • 16 PCBs per tray (8×2 layout) • Multiple trays stacked vertically • Motorised elevator lifts tray to pick level • Separate input magazines for NFC / NON-NFC variants
[6 empty] | ↓ | Robot lifts top tray to pick area
[5 empty] | ROBOT ARM + GRIPPER |  |  |  | • 6-axis / SCARA robot • 4-finger or vacuum cup gripper • Picks 2 or 4 PCBs per cycle (TBD) • Repeatability target: ±0.1 mm
↓
② ALIGNMENT & 2D BARCODE SCAN
◄ | ALIGNMENT JIG |  |  | ←→ | • Robot places 4 PCBs onto alignment JIG • 1 scanner reads all 4 × 2D codes simultaneously • Barcode IDs linked to slots 1-4 • Scan position: at JIG (per design memo) |  |  | ←→ | 2D BARCODE SCANNER KEYENCE SR-X100W / SR-700
[6 empty] | ↓ | All 4 barcodes read OK?
[5 empty] | DECISION: Barcodes Valid? |  |  | ✗ → FAIL: robot moves to fail tray
↓
③ FIXTURE LOADING (Robot arm places PCBs)
| FIXTURE 1 Left Type 4 Slots |  |  |  | Robot places 4 PCBs simultaneously into each fixture • Pneumatic actuator closes fixture lid • Pogo pins contact PCB test pads • Fixture type selected: NFC or NON-NFC (Left / Right) • Clamping force: TBD (N) |  |  |  | FIXTURE 2 Right Type 4 Slots
|  |  |  | ←→ |  |  |  | ←→
↓
④ FCT TEST EXECUTION
| PLC (BANWA — Thailand) Signals to FCT PC: → FCT_START ← FCT_READY ← SLOT_PASS[1-4] ← SLOT_FAIL[1-4] ← FCT_DONE ← FCT_ERROR |  |  |  | FCT TEST PC (INDIA — NFC_Rev3.01 updated) • orchestrator.py 4-slot parallel threads • integrated_automation.py • per-slot: T32 + PSU + CAN + LIN • pc_io_interface.py (PLC I/F) • Barcode scanner driver • CSV + HTML result logger • gui_main.py (4-slot display) |  |  |  | TEST INSTRUMENTS (per 4-slot operation) • 4× KIKUSUI PWR401L (PSU per slot, VISA/USB) • 4× Lauterbach Trace32 (PowerDebug E40 + DC20A) • PCAN-USB Pro FD ×2 (4 CAN channels total) • PLIN-USB (LIN interface) • KEYENCE SR-X100W (2D barcode scanner)
|  |  |  | ⇔ |  |  |  | ⇔
↓
④-a TEST SEQUENCE PER SLOT (runs in parallel across all 4 slots)
| HW SETUP T32 connect PSU on | LED RGB on/off voltage verify | BATTERY ADC read voltage check | MOTOR OCP test actuate | EOS offset/zero process | SG 1+2 Strain Gauge OpAmp verify | CAPA Capacitive sensor | NFC read/write verify | CAN bus comm PCAN | LIN bus comm PLIN | RESULT PASS/FAIL CSV+HTML
| → | → | → | → | → | → | → | → | → | →
↓
⑤ RESULT SORTING & OUTPUT
DECISION: Per-Slot PASS / FAIL?
|  |  | ↓ PASS |  |  | ↓ |  |  | ↓ FAIL
| PASS TRAY (OK parts) ✓ Slot result = PASS |  |  |  | ROBOT ARM Removes PCBs from fixture (sorted by slot result) |  |  |  | FAIL TRAY (NG parts) ✗ Slot result = FAIL
|  |  |  | ← |  |  |  | →
⑥ LOOP — Robot picks next batch. Empty tray moved. Full output tray swapped by operator.
LEGEND
| Hardware / Mechanical |  |  | FCT Software (INDIA scope) |  |  | PLC / I/O Signal (BANWA) |  |  | Instruments

## Condition
Base design: |  | Manual handling 1pcs system control (FW, SW)
Modefy points |  | [ Fit for autohandling system ]
Sytem image at sheet " FCT autohandling design memo "
Test four targets simultaneously on a single PC.
|  | CAN / LIN tool |  | at sheet " FCT tool list (Main Equip.) "
2D scanner
add control design for handling machine timming control (PLC)
FCT START trigger
FCT FINISH trigger
OK(PASS) / FAIL sign
ERROR sign
others
data logging extract,
each item CSV file format, (continue html file,continue no problem)
reason: for pick-up our server.

## FCT tool list (Main Equip.)
ITEM | MAKER | MODEL | MEMO
Barcode scanner | KEYENCE | SR-X100 or SR-X100W | USB (USB-COM) type .
or
SR-700
CAN tool | PEAK | PCAN-USB Pro FD | Design debug timing, buy yourself, after we buy it if can.
LIN tool | PEAK | PLIN-USB
PowerSupply | KIKUSUI | PWR401L | VISA control. USB
Debugger | LAUTERBACH | PowerDebug E40 LA-3503 | Debugger tool no change
Debugger Coretex-M (Arm6/7/8) DC20A (PACK) LA-3254
Arm Converter IDC20A to MIPI-10/20D/34 LA-3770
PC set |  |  | 1PC control 4set

## FCT autohandling design memo
PCBAは 8x2 = 16個入りトレイに同じ向きで入っている
トレイは複数個積み上げられている
一番上のトレイを持ち上げて 取り出しエリアにおく
PCBAの取り出しは取り出しエリアにて行う
空トレイになったらトレイを 別の所に置くアクションを行う、
※検査後のトレイ収納も同じ考え方
OK/NGの仕分け
Alignment JIG ( Waiting to INPUT and OUTOUT)
1tray pick-up from stacked. | Arrow are |  |  |  | " Rotation "
| Robot, arm control (image) |  |  |  | 2JIG for INPUT (2_PCBA are on), 2D code scan here
Pick up 2pcs set to alig-JIG |  | Emply (not hold) action |  |  | 2JIG for OUTPUT (Not on PCBA) after FCT 2_PCBA on |  |  | OPEN / CLOSE action
Hold on action
Scan 2D code （1scanner read 4pcs 1time action)
|  | Pick up 1 tray | Set to Ali-JIG
Set to FIxture
Do FCT
Take out from fixture
Down to select stage | [6 empty] | Fixture [2pcs set] x2 set
Design reason for ProbePin fitting and maintenance
Select OK / NG pick-up | [5 empty] | FCT tester, 1PC control to 4pcs
set to finish tray
TRAY
8x2 [pcs]
Pick-up stage
(1-tray set)
Aligment JIG (a)
2 pcs
Aligment JIG (b)
2 pcs
Aligment JIG (c)
2 pcs
Aligment JIG (d) 2 pcs
FCT_tester (Fixture)
INPUT
OUTPUT
FIXTURE
[ BED of NAIL ]
FIXTURE
[ BED of NAIL ]
FIXTURE
[ BED of NAIL ]
FIXTURE
[ BED of NAIL ]
" After " stage (Select stage)
PASS (OK)
FAIL (NG)
NG TRAY
OK TRAY
2D_code acanner (1 scanner read 4 pcs data)

## Flow - India
INDIA TEAM SCOPE — DETAILED DESIGN: I/F I/O Signal Design + FCT Software Architecture
Activity: (1) I/F I/O signal spec between PLC-BANWA and FCT-PC-INDIA ¦ (2) FCT inspection program update: 4-slot parallel ¦ Base: Rev3.01
PART A — I/F I/O SIGNAL DESIGN (Collaborative: INDIA designs spec, BANWA implements PLC side)
| PLC — BANWA (Thailand) | I/O | FCT TEST PC — INDIA (Rev3.01)
| FCT_START | → (PLC to FCT PC) | PLC triggers FCT test start. Pulse width: TBD ms.
| FCT_READY | ← (FCT PC to PLC) | FCT PC signals it is initialised and waiting for PCBs.
| FIXTURE_CLOSED | → (PLC to FCT PC) | PLC confirms fixture pneumatic closure complete.
| BARCODE_DATA / LINK | → or USB direct | Scanned 2D barcode IDs linked to slots 1-4. Path: TBD.
| SLOT_PASS[1] | ← (FCT PC to PLC) | Slot 1 test result = PASS. PLC releases slot 1 PCB.
| SLOT_PASS[2] | ← (FCT PC to PLC) | Slot 2 test result = PASS.
| SLOT_PASS[3] | ← (FCT PC to PLC) | Slot 3 test result = PASS.
| SLOT_PASS[4] | ← (FCT PC to PLC) | Slot 4 test result = PASS.
| SLOT_FAIL[1] | ← (FCT PC to PLC) | Slot 1 test result = FAIL. PLC routes slot 1 PCB to fail tray.
| SLOT_FAIL[2] | ← (FCT PC to PLC) | Slot 2 test result = FAIL.
| SLOT_FAIL[3] | ← (FCT PC to PLC) | Slot 3 test result = FAIL.
| SLOT_FAIL[4] | ← (FCT PC to PLC) | Slot 4 test result = FAIL.
| FCT_DONE | ← (FCT PC to PLC) | All 4 slots complete. Robot arm may open fixture.
| FCT_ERROR | ← (FCT PC to PLC) | FCT software error (T32 fail, PSU fail, etc). PLC holds robot.
Physical Interface: USB-Relay module / Modbus TCP / EtherNet/IP (TBD per Q4, Q5) ¦ Voltage Level: 24 V DC or 5 V DC (TBD per Q5) ¦ Timing: pulse width / hold time TBD per Q6, Q7 ¦ Handshake protocol: TBD per Q8
PART B — FCT SOFTWARE ARCHITECTURE (INDIA solo — 4-slot parallel execution)

## Questions - India
TECHNICAL QUESTIONS — INDIA TEAM SCOPE (I/F I/O Design + FCT Program)
Activity: (1) I/F I/O design [Collaborative INDIA+BANWA] ¦ (2) FCT inspection program update for 4-PCB auto-handling [INDIA] ¦ Base code: Rev3.01
SECTION 1 — I/F I/O SIGNAL DEFINITION (Collaborative: INDIA , BANWA implements PLC side)
No. | Category | Question | Background / Why needed | Expected Answer Format | Priority | Answer / Status
1 | Signal List | What is the complete list of signals FCT PC must OUTPUT to PLC? Proposed: FCT_READY, FCT_DONE, SLOT_PASS[1-4], SLOT_FAIL[1-4], FCT_ERROR | Defines PLC input module wiring. | Signal name list + direction + logical state | HIGH
2 | Signal List | What is the complete list of signals FCT PC must RECEIVE from PLC? Proposed: FCT_START, PCB_IN_SLOT[1-4], FIXTURE_CLOSED | Defines which PLC output signals trigger FCT software actions. | Signal name list + direction + trigger condition | HIGH
3 | Granularity | Are PASS/FAIL signals per-slot (4 individual signals) or per-fixture (one combined signal after all 4 PCBs done)? | Per-slot allows PLC to release each slot independently after its test. | Decision: per-slot OR per-fixture | HIGH
4 | Physical I/F | What physical interface carries signals between test PC and PLC — USB-relay, PCIe I/O card, or Ethernet protocol (Modbus TCP / EtherNet/IP)? | Choice drives Python driver library selection. | Interface type + model/protocol | HIGH
5 | Voltage Level | Signal voltage level: 24 V DC (industrial standard) or 5 V DC (PC GPIO)? | If 24 V: USB-relay or optocoupler isolation needed. | Voltage level (V DC) + sink/source type | HIGH
6 | Timing: START | What is the minimum FCT_START pulse width (ms) the FCT PC must detect? Minimum hold time before PCB confirmed seated? | Python polling interval must be ≤ half minimum pulse width to ensure reliable detection. | Numeric: pulse width ms + hold time ms | HIGH
7 | Timing: DONE | How long must FCT_DONE (PASS/FAIL) stay asserted so PLC scan cycle can read it reliably? | PLC scan cycle time determines minimum hold time needed. | Numeric: hold time ms | MED
8 | Handshake | Is a handshake required? E.g. PLC→FCT_START → FCT PC asserts FCT_ACK → PLC releases FCT_START → test begins? | Without handshake, PLC pulse shorter than Python poll interval may be missed. | Protocol description or state machine sketch | HIGH
9 | ERROR Recovery | After FCT_ERROR, what PLC action — pause robot, wait for manual clear, or auto-retry? What signal clears the error from FCT PC? | Prevents robot placing next PCB into an error slot. | Recovery sequence description | HIGH
10 | READY Signal | Should FCT PC send FCT_READY to PLC when software is fully initialised and waiting? | PLC must not send FCT_START before Trace32/PSU/PCAN are ready. | Yes/No + signal behaviour | MED
11 | Barcode Data Path | Does 2D scanner (KEYENCE SR-X100/SR-700) connect directly to FCT test PC via USB, or does PLC read barcode and pass ID to FCT PC via shared register? | Current Rev3.01 already has scan_code field. Direct USB-to-PC is simplest. | Decision: direct USB to FCT PC OR via PLC data channel | HIGH
12 | Slot Identity | How does FCT PC map each scanned barcode to a fixture slot (1-4) — slot-ID encoding in START trigger, or scanning order = slot order? | Needed to correctly label each result row in the CSV with the right barcode ID. | Slot-ID encoding scheme or scan order convention | HIGH
13 | I/O Spec Doc Owner | Who owns the I/O Signal Interface Specification document ? | Must be baselined before BANWA's PLC program starts. | Ownership decision | MED
14 | 2 Fixture Types | Both fixture types (Left/Right or NFC/NON-NFC) — do they share the same FCT_START/DONE signals, or each has independent signal set? | Affects total I/O count and whether FCT SW needs to know active fixture type. | Shared or independent signal sets per fixture type | MED
SECTION 2 — FCT INSPECTION PROGRAM: 4-PCB PARALLEL ARCHITECTURE (INDIA base Rev3.01)

## Quotation - India
QUOTATION REQUEST — INDIA TEAM SCOPE: I/F I/O Design + FCT Inspection Program Update
Prepared by | Charan Singh / INDIA team |  | Project: | XNF FCT Auto-Handling
Date: | 2026-06-09 |  | Doc No.: | 1
Base FCT Code: | Rev3.01 |  | PCB Model: | i460 NFC + NON-NFC
Schedule Ref.: | XNF FCT Automation Schedule TBD |  | Target: | 4-PCB parallel, 2 fixture types
Rev.: | 0 |  | Status: | DRAFT — pending TQ answers
SCOPE: | INDIA software activities ONLY. Excluded: hardware, robot arm, PLC program
PHASE 1 — I/F I/O SIGNAL DESIGN (Collaborative)
Item | Work Item / Deliverable | Scope Description | Unit | Rate | Total | Remarks / Dependencies
1-01 | I/O Signal Interface Spec Document | Define all signals: names, direction, voltage, timing, handshake protocol between FCT PC and PLC (both fixture types). Agree with BANWA before their PLC program starts. | Doc | TBD | TBD
1-02 | Signal Verification Test Plan | Define loopback test + timing verification plan to confirm correct I/O signal behaviour once BANWA PLC side is ready. | Doc | TBD | TBD
1-03 | Python I/O Driver | Implement Python driver for chosen physical interface (USB-relay / Modbus TCP — TBD per Q4/Q5). API: wait_for_start(slot), send_pass(slot), send_fail(slot), send_error(slot), send_ready(). | Lot | TBD | TBD
1-04 | I/O Integration Test with BANWA PLC | Joint session: verify all signals trigger correct PLC actions. Debug timing issues. Remote or on-site | Lot | TBD | TBD
PHASE 2 — FCT INSPECTION PROGRAM (INDIA 4-slot parallel)
Item | Work Item / Deliverable | Scope Description | Unit | Rate | Total | Remarks / Dependencies
2-01 | 4-Slot Parallel Execution Architecture | 4 concurrent test threads/processes. Thread-safe resource allocation for Trace32, PSU, PCAN, PLIN per slot. Slot management + per-slot state machine. | Lot | TBD | TBD
2-02 | Lauterbach Multi-Probe Management | Update Functional/trace32.py + HardwareSetupVerifier for 4 independent Trace32 instances (per-slot port numbers, separate script sessions, connect/go/disconnect per slot). | Lot | TBD | TBD
2-03 | PSU Per-Slot Control (4 VISA instances) | Update power_supply.py for 4 KIKUSUI VISA addresses. Each slot gets independent supply on/off/measure. Handles supply_on_wait (5s) and supply_off_wait (2s) per slot. | Lot | TBD | TBD
2-04 | PCAN + PLIN Per-Slot Channel Assignment | Update can_service.py / lin_service.py to bind each slot to its PCAN channel (slot1→ch1, slot2→ch2, etc.) and PLIN port. Validate with 4-PCB simultaneous CAN/LIN traffic. | Lot | TBD | TBD
2-05 | PCB Variant Auto-Selection per Slot | Extend GUI and automation runner to accept NFC/NON-NFC variant assignment per slot. Passes correct Trace32 preset (1 or 2) to each slot thread independently. | Lot | TBD | TBD
2-06 | PLC Start Trigger Integration | Replace GUI Play-button trigger with PLC FCT_START signal listener. Slot test starts when pc_io_interface (1-03) detects FCT_START for that slot. | Lot | TBD | TBD
2-07 | CAPA Test — Auto Fixture Adaptation | Verify/adapt DigitalSwitchController for automated fixture. If physical capacitive switch is actuated by fixture mechanism, confirm signal path. Update test step if behaviour changes. | Lot | TBD | TBD
2-08 | Per-Slot PASS/FAIL Signal Output | After each slot completes test, call send_pass(slot)/send_fail(slot) via pc_io_interface so PLC can release that slot to the pass/fail sorter. | Lot | TBD | TBD
PHASE 3 — BARCODE SCANNER INTEGRATION + DATA LOGGING
Item | Work Item / Deliverable | Scope Description | Unit | Rate | Total | Remarks / Dependencies
3-01 | Barcode Scanner Driver | KEYENCE SR-X100/SR-700 USB-COM serial reader in Python. Map each scanned 2D code to its fixture slot. Trigger scan at correct point in test flow. | Lot | TBD | TBD
3-02 | Per-Slot CSV Result Logger | Per-PCB CSV with: barcode ID, slot no., variant, date-time, all test items (measured + PASS/FAIL), overall PASS/FAIL. File naming per agreed convention. | Lot | TBD | TBD
3-03 | HTML Report Update | Update html_report_generator.py for combined 4-slot batch report OR confirm per-PCB report is sufficient. | Lot | TBD | TBD
3-04 | MySQL Logging Module (conditional) | If YES: implement MySQL INSERT per test result row with barcode traceability. Connection pooling, error handling. | Lot | TBD | TBD
PHASE 4 — GUI UPDATE + SYSTEM TESTING + DOCUMENTATION
Item | Work Item / Deliverable | Scope Description | Unit | Rate | Total | Remarks / Dependencies
4-01 | 4-Slot Status GUI (gui_main.py) | Update GUI to show 4 independent slot panels: scan code input, test progress, per-test status, PASS/FAIL indicator. All 4 running simultaneously. | Lot | TBD | TBD
4-02 | System Integration & Timing Verification | End-to-end test of all 4 slots simultaneously. Verify I/O timing, barcode traceability, CSV output, PASS/FAIL sorting signal. On-site or remote per | Lot | TBD | TBD
4-03 | Acceptance Test Execution | Run official acceptance batch (agreed PCB count + scenario coverage) with production team. Document results, obtain sign-off for 'FCT review' milestone. | Lot | TBD | TBD
4-04 | Software Design Document Update | Update SDD to reflect 4-slot architecture, I/O driver design, new data logging flow, and any test sequence changes. | Doc | TBD | TBD
EFFORT SUMMARY (BASE ESTIMATE)
Phase 1 — I/F I/O Signal Design |  |  | BANWA PLC implementation + INDIA Team
Phase 2 — FCT Core (4-slot parallel) |  |  | Largest block; depends on TQ architecture answers
Phase 3 — Barcode + Data Logging |  |  | TBD days if MySQL required
Phase 4 — GUI + Testing + Documentation |  |  | TBD days
TOTAL (base, excl. MySQL) |  |  | ~
SCOPE BOUNDARY NOTES:
1. EXCLUDED: hardware (fixtures/robot/conveyor/tray handlers), PLC program (BANWA scope), Lauterbach/PCAN/PLIN hardware purchases, KEYENCE scanner purchase.
2. All estimates final figures after TQ-India answers received.
3. Item MySQL conditional — add TBD days if confirmed YES.
4. Phase 2 assumes 4x Lauterbach probes + 4x PSU available before integration testing starts.