## System Overview (hidden)
System Overview — Conveyor-Fed Automatic PCB Test Station
┌─────────────────────────────────────────────────────────────────────────────────────────────────┐
│ CONVEYOR-FED AUTOMATIC PCB TEST STATION — SYSTEM OVERVIEW │
└─────────────────────────────────────────────────────────────────────────────────────────────────┘
[UPSTREAM CONVEYOR] ──► [ENTRY STOPPER ↑] ──► [BARCODE SCANNER] ──► [PRESS STATION] ──► [EXIT]
│
┌──────────┴──────────┐
│ PNEUMATIC PRESS │
│ (Top plate + pogo │
│ pin carrier down) │
│ + Connector plug-in │
└──────────┬──────────┘
│
┌──────────┴──────────┐
│ TEST INSTRUMENTS │
│ • KIKUSUI PWR401L │
│ • Lauterbach Trace32│
│ • PCAN-USB (CAN) │
│ • PLIN-USB (LIN) │
└──────────┬──────────┘
│
┌──────────┴──────────┐
│ TEST PC │
│ orchestrator.py │
│ gui_main.py │
│ MySQL logging │
│ HTML report │
└──────────┬──────────┘
│
PASS ◄───────────────┼───────────────► FAIL
│ │
[EXIT CONVEYOR] [REJECT TRAY]

## Condition
Base design: |  | Manual handling 1pcs system control (FW, SW)
Modefy points |  | [ Fit for autohandling system ]
Sytem image at sheet " FCT autohandling design memo "
Test four targets simultaneously on a single PC.
|  | CAN / LIN tool |  | at sheet " FCT tool list (Main Equip.) "
2D scanner
add control design for handling machine timming control (PLC)
FCT START trigger
FCT FINISH trigger
OK(PASS) / FAIL sign
ERROR sign
others
data logging extract,
each item CSV file format, (continue html file,continue no problem)
reason: for pick-up our server.

## FCT tool list (Main Equip.)
ITEM | MAKER | MODEL | MEMO
Barcode scanner | KEYENCE | SR-X100 or SR-X100W | USB (USB-COM) type .
or
SR-700
CAN tool | PEAK | PCAN-USB Pro FD | Design debug timing, buy yourself, after we buy it if can.
LIN tool | PEAK | PLIN-USB
PowerSupply | KIKUSUI | PWR401L | VISA control. USB
Debugger | LAUTERBACH | PowerDebug E40 LA-3503 | Debugger tool no change
Debugger Coretex-M (Arm6/7/8) DC20A (PACK) LA-3254
Arm Converter IDC20A to MIPI-10/20D/34 LA-3770
PC set |  |  | 1PC control 4set

## FCT autohandling design memo
PCBAは 8x2 = 16個入りトレイに同じ向きで入っている
トレイは複数個積み上げられている
一番上のトレイを持ち上げて 取り出しエリアにおく
PCBAの取り出しは取り出しエリアにて行う
空トレイになったらトレイを 別の所に置くアクションを行う、
※検査後のトレイ収納も同じ考え方
OK/NGの仕分け
Alignment JIG ( Waiting to INPUT and OUTOUT)
1tray pick-up from stacked. | Arrow are |  |  |  | " Rotation "
| Robot, arm control (image) |  |  |  | 2JIG for INPUT (2_PCBA are on), 2D code scan here
Pick up 2pcs set to alig-JIG |  | Emply (not hold) action |  |  | 2JIG for OUTPUT (Not on PCBA) after FCT 2_PCBA on |  |  | OPEN / CLOSE action
Hold on action
Scan 2D code （1scanner read 4pcs 1time action)
|  | Pick up 1 tray | Set to Ali-JIG
Set to FIxture
Do FCT
Take out from fixture
Down to select stage | [6 empty] | Fixture [2pcs set] x2 set
Design reason for ProbePin fitting and maintenance
Select OK / NG pick-up | [5 empty] | FCT tester, 1PC control to 4pcs
set to finish tray
TRAY
8x2 [pcs]
Pick-up stage
(1-tray set)
Aligment JIG (a)
2 pcs
Aligment JIG (b)
2 pcs
Aligment JIG (c)
2 pcs
Aligment JIG (d) 2 pcs
FCT_tester (Fixture)
INPUT
OUTPUT
FIXTURE
[ BED of NAIL ]
FIXTURE
[ BED of NAIL ]
FIXTURE
[ BED of NAIL ]
FIXTURE
[ BED of NAIL ]
" After " stage (Select stage)
PASS (OK)
FAIL (NG)
NG TRAY
OK TRAY
2D_code acanner (1 scanner read 4 pcs data)

## TQ - India Scope
TECHNICAL QUESTIONS — INDIA TEAM SCOPE (I/F I/O Design + FCT Program Update)
Activity: (1) I/F I/O design [Collaborative INDIA+BANWA] ¦ (2) FCT inspection program update for 4-PCB auto-handling [INDIA solo] ¦ Base code: NFC_Rev3.01
SECTION 1 — I/F I/O SIGNAL DEFINITION (Collaborative: INDIA designs spec, BANWA implements PLC side)
No. | Category | Question | Background / Why needed | Expected Answer Format | Direction | Priority | Answer / Status
1 | Signal List | What is the complete list of signals FCT PC must OUTPUT to PLC? Proposed: FCT_READY, FCT_DONE, SLOT_PASS[1-4], SLOT_FAIL[1-4], FCT_ERROR | Defines PLC input module wiring. INDIA must propose list; BANWA must accept it. | Signal name list + direction + logical state | INDIA→BANWA | HIGH
2 | Signal List | What is the complete list of signals FCT PC must RECEIVE from PLC? Proposed: FCT_START, PCB_IN_SLOT[1-4], FIXTURE_CLOSED | Defines which PLC output signals trigger FCT software actions. | Signal name list + direction + trigger condition | BANWA→INDIA | HIGH
3 | Granularity | Are PASS/FAIL signals per-slot (4 individual signals) or per-fixture (one combined signal after all 4 PCBs done)? | Per-slot allows PLC to release each slot independently after its test. | Decision: per-slot OR per-fixture | BANWA decide | HIGH
4 | Physical I/F | What physical interface carries signals between test PC and PLC — USB-relay, PCIe I/O card, or Ethernet protocol (Modbus TCP / EtherNet/IP)? | Choice drives Python driver library selection. | Interface type + model/protocol | BANWA propose | HIGH
5 | Voltage Level | Signal voltage level: 24 V DC (industrial standard) or 5 V DC (PC GPIO)? | If 24 V: USB-relay or optocoupler isolation needed. Affects INDIA hardware spec. | Voltage level (V DC) + sink/source type | BANWA | HIGH
6 | Timing: START | What is the minimum FCT_START pulse width (ms) the FCT PC must detect? Minimum hold time before PCB confirmed seated? | Python polling interval must be ≤ half minimum pulse width to ensure reliable detection. | Numeric: pulse width ms + hold time ms | BANWA define | HIGH
7 | Timing: DONE | How long must FCT_DONE (PASS/FAIL) stay asserted so PLC scan cycle can read it reliably? | PLC scan cycle time determines minimum hold time needed. | Numeric: hold time ms | BANWA define | MED
8 | Handshake | Is a handshake required? E.g. PLC→FCT_START → FCT PC asserts FCT_ACK → PLC releases FCT_START → test begins? | Without handshake, PLC pulse shorter than Python poll interval may be missed. | Protocol description or state machine sketch | Agree together | HIGH
9 | ERROR Recovery | After FCT_ERROR, what PLC action — pause robot, wait for manual clear, or auto-retry? What signal clears the error from FCT PC? | Prevents robot placing next PCB into an error slot. | Recovery sequence description | BANWA decide + INDIA implement | HIGH
10 | READY Signal | Should FCT PC send FCT_READY to PLC when software is fully initialised and waiting? | PLC must not send FCT_START before Trace32/PSU/PCAN are ready. | Yes/No + signal behaviour | Agree together | MED
11 | Barcode Data Path | Does 2D scanner (KEYENCE SR-X100/SR-700) connect directly to FCT test PC via USB, or does PLC read barcode and pass ID to FCT PC via shared register? | Current NFC_Rev3.01 already has scan_code field. Direct USB-to-PC is simplest. | Decision: direct USB to FCT PC OR via PLC data channel | Agree together | HIGH
12 | Slot Identity | How does FCT PC map each scanned barcode to a fixture slot (1-4) — slot-ID encoding in START trigger, or scanning order = slot order? | Needed to correctly label each result row in the CSV with the right barcode ID. | Slot-ID encoding scheme or scan order convention | Agree together | HIGH
13 | I/O Spec Doc Owner | Who owns the I/O Signal Interface Specification document — INDIA drafts + BANWA reviews, or BANWA drafts + INDIA reviews? | Must be baselined before BANWA's PLC program starts (schedule: '26_7). | Ownership decision | BANWA/INDIA | MED
14 | 2 Fixture Types | Both fixture types (Left/Right or NFC/NON-NFC) — do they share the same FCT_START/DONE signals, or each has independent signal set? | Affects total I/O count and whether FCT SW needs to know active fixture type. | Shared or independent signal sets per fixture type | BANWA define | MED
SECTION 2 — FCT INSPECTION PROGRAM: 4-PCB PARALLEL ARCHITECTURE (INDIA solo — base NFC_Rev3.01)
No. | Category | Question | Background / Why needed | Expected Answer Format | Direction | Priority | Answer / Status
15 | Architecture | 4-slot parallel: use (a) 4 independent Python processes (each with own Trace32/PSU/PCAN) or (b) one process with 4 threads sharing controllers? | Option (a) is isolated; option (b) is lighter but needs thread-safe orchestrator.py refactor. | Decision: multi-process OR multi-thread | INDIA decide | HIGH
16 | T32: Multi-Probe | Does the Lauterbach setup support 4 simultaneous debug connections? Current: 1x PowerDebug E40 + DC20A. If 4-PCB parallel flash needed: 4 probes + 4 licenses required. | If sequential flash is acceptable, one probe with time-multiplexed connections reduces hardware cost. | Simultaneous (4 probes) OR sequential flash (1 probe) | INDIA verify + Lauterbach | HIGH
17 | T32: Python API | Can Functional/trace32.py be instantiated 4 times simultaneously? Current code uses global t32.dbg. Multi-slot needs per-slot Trace32Interface with separate port numbers. | Core dependency for parallel execution architecture. | Yes/No + required changes to trace32.py | INDIA verify | HIGH
18 | PSU: Per-slot | Max current per RH_i460 PCB under test (A)? Can 1x KIKUSUI PWR401L (40 V / 1 A) supply all 4 PCBs? Or 1 PSU per slot = 4 units? | 4 PSUs need 4 VISA addresses. Significant cost impact. | Max current per PCB (A) + decision: shared or 4 units | INDIA verify HW spec | HIGH
19 | PCAN Channels | How many CAN channels does one RH_i460 PCB use during FCT? PCAN-USB Pro FD has 2 CAN FD channels — how many units needed for 4 PCBs? | Determines PCAN hardware procurement quantity. | CAN ch per PCB + total PCAN units needed | INDIA verify test spec | HIGH
20 | PLIN Channels | How many LIN channels per PCB during FCT? Can PLIN-USB time-multiplex 4 PCBs or is 1 unit per PCB needed? | Determines PLIN hardware qty. | LIN ch per PCB + total PLIN units needed | INDIA verify test spec | HIGH
21 | Variant per Slot | Can each slot independently select NFC (preset=2) or NON-NFC (preset=1), or must all 4 slots run same variant per batch? | Mixed-variant batches need per-slot variant selection in GUI and per-slot Trace32 script. | Same variant per batch OR independent per slot | INDIA + production | MED
22 | Start Trigger | In automated mode, what triggers FCT test start — PLC FCT_START signal (removing GUI Play button) or still GUI button? | If PLC-triggered: automation loop must watch I/O signal instead of GUI input. | PLC signal-triggered OR GUI-triggered | INDIA + BANWA | HIGH
23 | Sequence Changes | Which test steps in NFC_Rev3.01 (LED/BAT/Motor/EOS/SG/CAPA/NFC/CAN/LIN) need modification for automated fixture? E.g. CAPA test uses DigitalSwitchController — how is physical switch press automated? | CAPA step requires a physical capacitive switch actuation. Must be verified if auto fixture covers this or if test step needs change. | List of steps needing modification + proposed solution | INDIA review + BANWA | HIGH
24 | Test Duration | What is the measured end-to-end test time per PCB using NFC_Rev3.01 NORMAL timing profile? (Reference: supply_on=5s, bat_wait=5s, sg_measure=3s×2 → rough estimate ~60-90s?) | Required to calculate takt time and confirm 4-slot parallel meets production target. | Measured duration (s) in NORMAL profile | INDIA measure | HIGH
25 | Power Cycle | Between successive PCBs in the same slot, is a full PSU power cycle (supply_off=2s + supply_on=5s = ~7s) mandatory, or can it be skipped if the slot is already initialised? | Optimising this 7s saves ~7s per PCB per slot. High impact on takt. | Mandatory per-PCB cycle OR can skip on re-run | INDIA review | MED
SECTION 3 — DATA LOGGING & RESULT FORMAT (INDIA solo)
No. | Category | Question | Background / Why needed | Expected Answer Format | Direction | Priority | Answer / Status
26 | CSV Fields | Required fields in per-PCB CSV: Barcode ID, Slot No., Date-Time, Variant, each test item (measured + PASS/FAIL), overall PASS/FAIL? | Production server picks up CSV files. Field list must match server expectations. | CSV column list / sample row | INDIA + production | HIGH
27 | File Naming | Naming convention for result CSV files? Suggestion: YYYYMMDD_HHMMSS_<BarcodeID>_Slot<N>_<PASS¦FAIL>.csv | Server-side automation may depend on filename pattern. | File naming pattern | INDIA + production | MED
28 | MySQL | Is MySQL logging (in System Overview sheet) a firm requirement, or is CSV-only sufficient per Condition sheet? | MySQL adds ~2 days effort. Needs explicit YES/NO decision. | YES or NO | U-Shin decision | MED
29 | HTML Report | Should HTML report be per-PCB (current) or a combined 4-slot batch report? | Combined report more useful for operators but requires redesigning html_report_generator.py. | Per-PCB OR 4-slot combined | INDIA decide | MED
30 | Log Storage | Result files written to local PC path or network share on factory server? | If network share: UNC path must be available with write permission from test PC. | Path specification | Production team | MED
SECTION 4 — SCHEDULE & DELIVERABLES (INDIA planning)
No. | Category | Question | Background / Why needed | Expected Answer Format | Direction | Priority | Answer / Status
31 | I/F Spec Date | By what date must I/O Signal Interface Specification be finalised? (PLC program starts '26_7 — INDIA I/F design: 2-3 wks from '26_6) | BANWA cannot start PLC program until I/F is agreed. | Target date (YYYY-MM) | INDIA + BANWA | HIGH
32 | FCT Review Scope | FCT review = 2 months' — does this include validation on real PCBs with the new fixture, or only code update? | 2 months is tight if it includes on-site fixture integration. Scope must be defined. | Scope description + acceptance criteria | INDIA + HMM-HQ | HIGH
33 | Integration Test | Who conducts end-to-end integration test — INDIA on-site in Thailand or remote support with BANWA leading? | On-site is recommended for debugging I/F timing issues. | On-site / remote / BANWA-led | BANWA + INDIA | MED
34 | Acceptance Criteria | Acceptance criteria for updated FCT software — e.g. zero false-PASS rate, ≥99% barcode traceability, test time within takt? | Required to formally close 'FCT review' schedule item. | Acceptance criteria list | U-Shin / HMM-HQ | MED

## Quotation - India
QUOTATION REQUEST — INDIA TEAM SCOPE: I/F I/O Design + FCT Inspection Program Update
Prepared by (INDIA): | Charan Singh / INDIA team |  |  | Project: | XNF FCT Auto-Handling — INDIA activities only
Date: | 2026-06-09 |  |  | Doc No.:
Base FCT Code: | NFC_Rev3.01 |  |  | PCB Model: | RH_i460 NFC + NON-NFC
Schedule Ref.: | XNF FCT Automation Schedule 260602a — INDIA rows only |  |  | Target: | 4-PCB parallel, 2 fixture types
Rev.: | 0 |  |  | Status: | DRAFT — pending TQ answers
SCOPE: | INDIA software activities ONLY. Excluded: hardware, robot arm, PLC program (BANWA/outsource scope).
PHASE 1 — I/F I/O SIGNAL DESIGN (Collaborative: INDIA leads spec) ¦ Schedule: 2-3 weeks starting '26_6
Item | Work Item / Deliverable | Scope Description | Days | Unit | Rate | Total | Remarks / Dependencies
1-01 | I/O Signal Interface Spec Document | Define all signals: names, direction, voltage, timing, handshake protocol between FCT PC and PLC (both fixture types). Agree with BANWA before their PLC program starts. | 3 | Doc | TBD | TBD | Critical input to BANWA PLC design. Must be done before '26_7.
1-02 | Signal Verification Test Plan | Define loopback test + timing verification plan to confirm correct I/O signal behaviour once BANWA PLC side is ready. | 1 | Doc | TBD | TBD | Joint test with BANWA after PLC program is ready
1-03 | Python I/O Driver (pc_io_interface.py) | Implement Python driver for chosen physical interface (USB-relay / Modbus TCP — TBD per Q4/Q5). API: wait_for_start(slot), send_pass(slot), send_fail(slot), send_error(slot), send_ready(). | 3 | Lot | TBD | TBD | Depends on Q4 (interface type) and Q5 (voltage level) answers
1-04 | I/O Integration Test with BANWA PLC | Joint session: verify all signals trigger correct PLC actions. Debug timing issues. Remote or on-site per Q33 decision. | 2 | Lot | TBD | TBD | Needs BANWA PLC program ready first
PHASE 2 — FCT INSPECTION PROGRAM CORE UPDATE (INDIA solo — 4-slot parallel) ¦ Part of 2-month FCT review
Item | Work Item / Deliverable | Scope Description | Days | Unit | Rate | Total | Remarks / Dependencies
2-01 | 4-Slot Parallel Execution Architecture | Refactor orchestrator.py + integrated_automation.py for 4 concurrent test threads/processes. Thread-safe resource allocation for Trace32, PSU, PCAN, PLIN per slot. Slot management + per-slot state machine. | 5 | Lot | TBD | TBD | Core change. Depends on Q15 (arch decision) and Q17 (T32 API)
2-02 | Lauterbach Multi-Probe Management | Update Functional/trace32.py + HardwareSetupVerifier for 4 independent Trace32 instances (per-slot port numbers, separate script sessions, connect/go/disconnect per slot). | 4 | Lot | TBD | TBD | Depends on Q16 (probe count) and Q17 (API verification)
2-03 | PSU Per-Slot Control (4 VISA instances) | Update power_supply.py for 4 KIKUSUI VISA addresses. Each slot gets independent supply on/off/measure. Handles supply_on_wait (5s) and supply_off_wait (2s) per slot. | 2 | Lot | TBD | TBD | Straightforward if 4 separate PSU units confirmed (Q18)
2-04 | PCAN + PLIN Per-Slot Channel Assignment | Update can_service.py / lin_service.py to bind each slot to its PCAN channel (slot1→ch1, slot2→ch2, etc.) and PLIN port. Validate with 4-PCB simultaneous CAN/LIN traffic. | 3 | Lot | TBD | TBD | Depends on Q19 and Q20 channel count answers
2-05 | PCB Variant Auto-Selection per Slot | Extend GUI and automation runner to accept NFC/NON-NFC variant assignment per slot. Passes correct Trace32 preset (1 or 2) to each slot thread independently. | 2 | Lot | TBD | TBD | Depends on Q21 (variant-per-slot decision)
2-06 | PLC Start Trigger Integration | Replace GUI Play-button trigger with PLC FCT_START signal listener. Slot test starts when pc_io_interface (1-03) detects FCT_START for that slot. | 2 | Lot | TBD | TBD | Depends on 1-03. Q22 must confirm PLC-triggered mode.
2-07 | CAPA Test — Auto Fixture Adaptation | Verify/adapt DigitalSwitchController for automated fixture. If physical capacitive switch is actuated by fixture mechanism, confirm signal path. Update test step if behaviour changes. | 2 | Lot | TBD | TBD | Q23 — must test on real auto fixture. Risk item.
2-08 | Per-Slot PASS/FAIL Signal Output | After each slot completes test, call send_pass(slot)/send_fail(slot) via pc_io_interface so PLC can release that slot to the pass/fail sorter. | 1 | Lot | TBD | TBD | Quick integration once 2-01 and 1-03 are done
PHASE 3 — BARCODE SCANNER INTEGRATION + DATA LOGGING (INDIA solo)
Item | Work Item / Deliverable | Scope Description | Days | Unit | Rate | Total | Remarks / Dependencies
3-01 | Barcode Scanner Driver | KEYENCE SR-X100/SR-700 USB-COM serial reader in Python. Map each scanned 2D code to its fixture slot. Trigger scan at correct point in test flow. | 2 | Lot | TBD | TBD | Depends on Q11 (data path), Q12 (slot mapping), Q13 (scanner model)
3-02 | Per-Slot CSV Result Logger | Per-PCB CSV with: barcode ID, slot no., variant, date-time, all test items (measured + PASS/FAIL), overall PASS/FAIL. File naming per agreed convention. | 2 | Lot | TBD | TBD | Depends on Q26 (fields) and Q27 (naming convention)
3-03 | HTML Report Update | Update html_report_generator.py for combined 4-slot batch report OR confirm per-PCB report is sufficient. | 1 | Lot | TBD | TBD | Depends on Q29 decision. Low effort either way.
3-04 | MySQL Logging Module (conditional) | If Q28=YES: implement MySQL INSERT per test result row with barcode traceability. Connection pooling, error handling. | 2 | Lot | TBD | TBD | CONDITIONAL — only if confirmed required. Not in base total.
PHASE 4 — GUI UPDATE + SYSTEM TESTING + DOCUMENTATION
Item | Work Item / Deliverable | Scope Description | Days | Unit | Rate | Total | Remarks / Dependencies
4-01 | 4-Slot Status GUI (gui_main.py) | Update GUI to show 4 independent slot panels: scan code input, test progress, per-test status, PASS/FAIL indicator. All 4 running simultaneously. | 3 | Lot | TBD | TBD | Lower priority — implement after core test logic is stable
4-02 | System Integration & Timing Verification | End-to-end test of all 4 slots simultaneously. Verify I/O timing, barcode traceability, CSV output, PASS/FAIL sorting signal. On-site or remote per Q33. | 3 | Lot | TBD | TBD | Requires BANWA fixture + PLC to be ready
4-03 | Acceptance Test Execution | Run official acceptance batch (agreed PCB count + scenario coverage) with production team. Document results, obtain sign-off for 'FCT review' milestone. | 2 | Lot | TBD | TBD | Final milestone closure
4-04 | Software Design Document Update | Update SDD to reflect 4-slot architecture, I/O driver design, new data logging flow, and any test sequence changes. | 2 | Doc | TBD | TBD | Required project deliverable
EFFORT SUMMARY (BASE ESTIMATE)
Phase 1 — I/F I/O Signal Design |  |  | 9 | Excl. BANWA PLC implementation
Phase 2 — FCT Core (4-slot parallel) |  |  | 21 | Largest block; depends on TQ architecture answers
Phase 3 — Barcode + Data Logging |  |  | 5 | +2 days if MySQL required (item 3-04)
Phase 4 — GUI + Testing + Documentation |  |  | 10
TOTAL (base, excl. MySQL) |  |  | 45 | ~
SCOPE BOUNDARY NOTES:
1. EXCLUDED: hardware (fixtures/robot/conveyor/tray handlers), PLC program (BANWA scope), Lauterbach/PCAN/PLIN hardware purchases, KEYENCE scanner purchase.
2. All estimates in working days (1 engineer). Final figures after TQ-India answers received.
3. Item 3-04 (MySQL) conditional — add 2 days if confirmed YES (Q28).
4. Phase 2 assumes 4x Lauterbach probes + 4x PSU available before integration testing starts.
5. Travel cost for on-site integration test in Thailand (item 4-02) NOT included — quote separately.
6. Items 1-04 and 4-02 require BANWA PLC program to be ready before INDIA can complete them.

## Technical Questions
FCT AUTOMATION — TECHNICAL QUESTIONS FOR VENDOR / ENGINEERING TEAM (FULL AUTOMATION SCOPE)
SECTION 1 — FIXTURE DESIGN
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
1 | Fixture Design | What are the exact PCB outer dimensions (L x W x H) and mounting-hole positions for the auto fixture? | Fixture tray pocket and pogo-pin carrier must be designed to these dimensions. | Drawing or dimension table (mm) | HIGH | U-Shin
2 | Fixture Design | Is the new auto fixture for NFC PCB, NON-NFC PCB, or will it cover both variants? (Slide mentions '2 types fixtures — Left / Right type') | The slide mentions '2 types fixtures for Left type / Right type'. Clarify if NFC vs NON-NFC or Left/Right orientation. | One of: NFC only / NON-NFC only / Both variants | HIGH | U-Shin
3 | Fixture Design | What is the number, layout, and pitch of pogo pins per fixture slot? | Required to confirm Lauterbach/CAN/LIN/power contact reliability at the fixture. | Pin layout drawing and pin count | HIGH | Vendor
4 | Fixture Design | What actuator type closes the fixture — pneumatic cylinder, servo, or other? What is the specified clamping force (N) and stroke (mm)? | Pneumatic drive needs air pressure spec; servo needs torque spec. Critical for fixture open/close timing in PLC program. | Actuator spec sheet + force/stroke values | HIGH | Vendor
5 | Fixture Design | What is the required fixture open/close cycle time (seconds)? | Determines whether robot arm wait time is the bottleneck or the test time. | Numeric: target cycle time in sec | MED | Vendor
6 | Fixture Design | Does each of the 4 PCB slots in a fixture have independent electrical isolation, or are they bussed together? | If bussed, single power supply may suffice. If isolated, 4 x KIKUSUI PWR401L required. | Schematic or written description | HIGH | Vendor
SECTION 2 — ROBOT ARM / HANDLING
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
7 | Robot Arm / Handling | What robot arm model (6-axis / SCARA / delta) and maker is planned for the pick-and-place operation? | Robot reach, payload, and I/O protocol must be matched with alignment JIG and fixture. | Robot model number and spec sheet | HIGH | Vendor
8 | Robot Arm / Handling | What end-effector / gripper type is used — vacuum suction cup or mechanical 4-finger gripper? | Slide shows '4-finger (or other idea)'. Vacuum requires compressor; finger gripper needs PCB edge clearance on tray. | Gripper model/sketch + grip method | HIGH | Vendor
9 | Robot Arm / Handling | How many PCBs does the robot arm pick up and place per cycle — 1, 2, or 4? (Memo shows 'Pick up 2 pcs set to align-JIG') | Memo shows 'Pick up 2 pcs set to align-JIG'. Slide note says 'It's not always four'. Confirm the designed-in count. | Numeric: pcs per cycle | HIGH | U-Shin/Vendor
10 | Robot Arm / Handling | What is the robot-to-fixture placement repeatability spec (mm)? | If worse than ±0.2 mm the pogo pins may miss PCB test pads. | Numeric: ±X mm | HIGH | Vendor
11 | Robot Arm / Handling | How many input trays and how many stacked levels are supported? | Determines magazine/tray handler design and operator replenishment frequency. | Numeric: trays per stack, total PCB capacity | MED | Vendor
12 | Robot Arm / Handling | Is the tray handler integrated into the robot arm motion, or is it a separate conveyor/elevator mechanism? | Impacts overall footprint and PLC I/O count. | Architecture sketch or written description | MED | Vendor
SECTION 3 — 2D BARCODE SCANNER
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
13 | 2D Barcode Scanner | Is the KEYENCE SR-X100W (wide) or SR-700 model selected? What is the USB interface — USB-HID (keyboard emulation) or USB-COM (serial)? | Tool list shows 'USB (USB-COM) type'. Confirm to set up serial port in test PC software. | Model + interface type | HIGH | Vendor
14 | 2D Barcode Scanner | Can one scanner read all 4 PCB 2D codes in a single scan, or does the robot present each PCB separately to the scanner? | Slide: '1 scanner read 4 pcs 1 time action'. If simultaneous, scanner FOV must cover 4 codes. | Simultaneous 4 OR sequential 1-by-1 | HIGH | Vendor
15 | 2D Barcode Scanner | Where is the scan position in the workflow — on the tray, at the alignment JIG, or inside the fixture? | Memo states 'Scan 2D code at Alignment JIG section (idea)'. Confirm final decision. | Location sketch / description | MED | U-Shin
16 | 2D Barcode Scanner | What 2D code symbology is printed on the PCB — QR Code, Data Matrix, or other? | Scanner setting and reader library must match the code type. | Symbology name | MED | U-Shin
17 | 2D Barcode Scanner | How does a missing or unreadable barcode get handled — alarm, skip, or auto-reject to fail tray? | Must be defined in both PLC logic and FCT software. | Procedure description | MED | U-Shin
SECTION 4 — PLC / I/O INTERFACE
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
18 | PLC / I/O Interface | What PLC brand and model is planned (e.g. OMRON, Mitsubishi, Siemens, Keyence KV)? | Determines available communication protocols (Ethernet/IP, Modbus TCP, CC-Link, digital I/O). | PLC model number | HIGH | Vendor
19 | PLC / I/O Interface | What signal voltage level is used for I/O between the PLC and the test PC — 24 V DC, 5 V DC, or relay contact? | Test PC GPIO or USB-relay module must match PLC output rating. | Voltage level (V DC) + current sink/source capability | HIGH | Vendor
20 | PLC / I/O Interface | What is the exact list of I/O signals required between PLC and test PC per fixture? (FCT_START trigger, FCT_FINISH trigger, OK/PASS, NG_FAIL, ERROR sign, others) | The Condition sheet lists: FCT START trigger, FINISH trigger, OK/FAIL sign, ERROR sign, others. Full list needed for I/O module selection. | Signal list with direction (PLC→PC / PC→PLC) and type | HIGH | U-Shin/Vendor
21 | PLC / I/O Interface | What is the communication protocol between test PC and PLC — digital I/O card, USB relay, Modbus TCP, or Ethernet/IP? | Python test software needs the correct driver/library to be selected. | Protocol name and connection method | HIGH | Vendor
22 | PLC / I/O Interface | What are the timing tolerances for FCT START and FINISH trigger signals (ms)? | Test orchestrator needs to know minimum pulse width to detect the signal reliably. | Numeric: pulse width ms, hold time ms | MED | Vendor
SECTION 5 — TEST PC / SOFTWARE (4-PCB PARALLEL)
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
23 | Test PC Software | The current test program is designed for 1 PCB at a time. Will automation require 4 independent instances of the program running in parallel, or one instance managing 4 slots? | Architecture decision affects Lauterbach license count, COM port assignments, and database logging. | One of: 4 instances / 1 multi-thread instance | HIGH | U-Shin
24 | Test PC Software | How many Lauterbach Trace32 licenses and hardware debug probes are required for 4-PCB parallel firmware flashing/testing? | Current setup: 1x PowerDebug E40 + DC20A pack. If 4 PCBs in parallel each need a debug session, 4 probes needed. | Count of probes + license type | HIGH | U-Shin/Lauterbach
25 | Test PC Software | Can PCAN-USB Pro FD supply 4 independent CAN channels simultaneously (4 PCBs tested in parallel)? | PCAN-USB Pro FD has 2 CAN FD channels. May need 2 units for 4 PCBs, or network topology change. | Channel count and hardware qty required | HIGH | U-Shin
26 | Test PC Software | Is one KIKUSUI PWR401L per PCB required (4 units total), or can one unit power all 4 PCBs with current sharing? | Max current per PCB vs. PWR401L capacity. Affects procurement cost significantly. | Power budget per PCB (V, A) + PSU qty | HIGH | U-Shin
27 | Test PC Software | If one PCB fails a test step in the middle of a 4-PCB parallel run, should: (a) stop only that slot and continue other 3, or (b) stop all 4? | Affects test flow logic and PLC signalling for individual fixture release. | One of: (a) per-slot stop / (b) all stop | HIGH | U-Shin
28 | Test PC Software | What data logging format is required — CSV (per Condition sheet), HTML report, MySQL DB, or all three? | Condition sheet states CSV as primary. MySQL is in System Overview but not Condition sheet. | Explicit list of required output formats | MED | U-Shin
29 | Test PC Software | Should the barcode ID scanned at the alignment JIG be written into the test result record (CSV / DB) as the unit identifier? | Traceability requirement from production side. | Yes / No | MED | U-Shin
SECTION 6 — THROUGHPUT
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
30 | Throughput | What is the current single-PCB test time (start to finish, seconds)? | Needed to calculate takt time and assess whether 4-fixture parallel testing meets production target. | Numeric: seconds | HIGH | U-Shin
31 | Throughput | What is the target production takt time per PCB (units per hour)? | Determines number of automation lines and shift planning. | Numeric: pcs/hour | HIGH | U-Shin/Production
32 | Throughput | Is firmware flashing (Lauterbach) performed inside the automated fixture, or in a separate pre-process step? | Flash time can dominate takt. If flash is inside FCT fixture, fixture utilisation drops significantly. | One of: inside FCT / separate step | HIGH | U-Shin
SECTION 7 — SAFETY / INSTALLATION
No. | Category | Question | Purpose / Background | Expected Answer Format | Priority | Raised By | Answer / Status
33 | Safety / Installation | What safety standards must the automation cell comply with (e.g. ISO 10218, CE, local Thai factory safety rules)? | Determines safety light curtains, fencing, emergency stop requirements. | Standard names / certificate list | MED | Vendor
34 | Safety / Installation | What are the installation site constraints — floor area (m²), ceiling height, power supply (voltage/phase/ampere)? | Needed for mechanical layout and electrical panel design. | Site spec sheet or measurements | MED | Vendor
35 | Safety / Installation | What compressed air supply is available at the installation site (pressure bar, flow L/min)? | Pneumatic fixture actuators and possibly vacuum gripper require compressed air. | Numeric: bar available, outlet size | MED | Vendor

## Quotation
FCT AUTOMATION HANDLING SYSTEM — QUOTATION REQUEST (FULL AUTOMATION SCOPE)
Requested by: | U-Shin (Thailand) Ltd. |  |  | Project: | XNF FCT Auto-Handling System
Date: | 2026-06-09 |  |  | Document No.:
Base Design Ref.: | NFC_Rev3.01 (Manual 1-pcs FCT) |  |  | Target Qty / Fixture: | 4 PCBs per cycle (2 fixtures)
PCB Model: | RH_i460 NFC + NON-NFC variants |  |  | Location: | Thailand Factory
Revision: | 0 |  |  | Status: | DRAFT — Pending technical Q&A
Prepared by: | Charan Singh |  |  | Contact: | charangopala@gmail.com
A. SCOPE OF SUPPLY — HARDWARE
Item No. | Description | Specification / Requirement | Qty | Unit | Unit Price (THB) | Total Price (THB) | Lead Time (wks) | Remarks
A-01 | Auto FCT Fixture Unit (Left-type) | 4-slot pneumatic press, pogo-pin carrier. Designed for RH_i460 PCB layout. | 1 | Set | TBD | TBD | TBD
A-02 | Auto FCT Fixture Unit (Right-type) | 4-slot pneumatic press, mirror layout of Left-type. | 1 | Set | TBD | TBD | TBD
A-03 | Robot Arm + Controller | 6-axis / SCARA pick-and-place. Payload: TBD. Repeatability: ±0.1 mm target. | 1 | Set | TBD | TBD | TBD
A-04 | End-Effector (Gripper) | 4-finger mechanical gripper or vacuum cup array to match PCB size. | 1 | Set | TBD | TBD | TBD
A-05 | Alignment JIG | PCB pre-positioning stage for 2D code scan. 4-slot capacity. | 1 | Set | TBD | TBD | TBD
A-06 | 2D Barcode Scanner — KEYENCE SR-X100W or SR-700 | USB-COM interface. FOV to cover 4 PCBs simultaneously. | 1 | Unit | TBD | TBD | TBD
A-07 | Input Tray Stack Magazine | Capacity: ≥5 stacked trays (16 PCBs/tray = 80 PCBs). Motorised elevator. | 2 | Set | TBD | TBD | TBD
A-08 | Output Tray Sorter (PASS + FAIL lanes) | Separate tray lanes for OK and NG. Capacity: TBD. | 1 | Set | TBD | TBD | TBD
A-09 | PLC + I/O Module | Brand/model TBD. Min I/O: FCT_START, FCT_DONE, PASS, FAIL, ERROR per fixture. | 1 | Set | TBD | TBD | TBD
A-10 | Pneumatic Supply Unit | FRL unit, solenoid valves for fixture actuator. Pressure: TBD bar. | 1 | Set | TBD | TBD | TBD
A-11 | Safety Fencing + Light Curtain | ISO 10218 compliant. Emergency stop included. | 1 | Set | TBD | TBD | TBD
A-12 | Control Panel + HMI | Panel PC or touch HMI for PLC monitoring. 24 V DC panel. | 1 | Set | TBD | TBD | TBD
A-13 | Cable Management / Wiring Duct | All internal wiring, connectors, labelling. | 1 | Lot | TBD | TBD | TBD
A-14 | Mechanical Frame / Base | Welded steel frame with adjustable levelling feet, ESD surface. | 1 | Set | TBD | TBD | TBD
B. TEST INSTRUMENTS (ADDITIONAL FOR 4-PCB PARALLEL)
Item No. | Description | Specification / Requirement | Qty | Unit | Unit Price (THB) | Total Price (THB) | Lead Time (wks) | Remarks
B-01 | KIKUSUI PWR401L Power Supply (additional) | For 1-PSU-per-PCB configuration. 1 unit currently available. | 3 | Unit | TBD | TBD | TBD | Additional units needed if 4 PCBs run independently
B-02 | PCAN-USB Pro FD (PEAK) | 2 CAN FD channels/unit. Need 2 units for 4 PCBs (4 channels total). | 1 | Unit | TBD | TBD | TBD | 1 unit already owned; confirm ch count per PCB
B-03 | PLIN-USB (PEAK) | LIN master per PCB. Confirm if 1 unit can time-multiplex 4 PCBs. | TBD | Unit | TBD | TBD | TBD | Depends on LIN test parallelism decision
B-04 | Lauterbach PowerDebug E40 LA-3503 (additional) | 1 probe per PCB for parallel flash+debug. 1 unit currently available. | 3 | Unit | TBD | TBD | TBD | Additional probes if parallel flash required
B-05 | Lauterbach Trace32 License (multi-target) | Licence upgrade/addition for multi-core/multi-target session. | TBD | License | TBD | TBD | TBD | Confirm with Lauterbach sales
B-06 | USB Hub (Industrial, 7-port) | For barcode scanner, PCAN, PLIN, Trace32 USB connections. | 2 | Unit | TBD | TBD | TBD
B-07 | Relay / GPIO Interface Module (USB) | For FCT_START / FINISH / PASS / FAIL I/O signals to/from PLC. | 2 | Unit | TBD | TBD | TBD | e.g. USB-RLY08 or similar
C. SOFTWARE DEVELOPMENT & ENGINEERING SERVICES
Item No. | Description | Specification / Requirement | Qty | Unit | Unit Price (THB) | Total Price (THB) | Lead Time (wks) | Remarks
C-01 | FCT Software — 4-PCB Parallel Execution | Modify orchestrator.py / test_sequences.py to run 4 independent test threads. Independent Trace32, PCAN, PLIN, PSU instance per slot. | 1 | Lot | TBD | TBD | TBD | Based on NFC_Rev3.01
C-02 | PLC I/O Interface Module | Python driver for PLC I/O: FCT_START trigger receive, PASS/FAIL/ERROR signal output per slot. | 1 | Lot | TBD | TBD | TBD | Protocol TBD per Q18-Q21
C-03 | Barcode Scanner Integration | KEYENCE SR-X100/SR-700 USB-COM driver. Map scanned 2D ID to PCB slot. Write ID to test log. | 1 | Lot | TBD | TBD | TBD
C-04 | 4-PCB Data Logging (CSV + HTML Report) | Per-slot CSV result file with barcode ID, timestamps, all test item results. Combined HTML report. | 1 | Lot | TBD | TBD | TBD | Current single-PCB report as base
C-05 | MySQL Database Integration (Optional) | Log results to central MySQL DB for traceability and SPC. | 1 | Lot | TBD | TBD | TBD | Confirm if required (see Q28)
C-06 | Test Sequence GUI Update | Update gui_main.py to show 4-slot status simultaneously. Per-slot START/STOP/RESULT display. | 1 | Lot | TBD | TBD | TBD
C-07 | PLC Program (Ladder / Structured Text) | Robot arm sequencing, fixture open/close, tray handling, I/O with test PC. Includes safety interlock. | 1 | Lot | TBD | TBD | TBD | BANWA scope / external vendor
C-08 | System Integration & Commissioning | On-site integration test, timing calibration, handoff documentation. | 1 | Lot | TBD | TBD | TBD | At Thailand factory
C-09 | Test Run & Acceptance | Run with production PCBs. Verify PASS/FAIL sorting accuracy. Sign-off protocol. | 1 | Lot | TBD | TBD | TBD
D. COST SUMMARY
Section A — Hardware (Fixture + Robot + Handling) | [5 empty] | TBD
Section B — Test Instruments (Additional) | [5 empty] | TBD
Section C — Software & Engineering Services | [5 empty] | TBD
Contingency (10%) | [5 empty] | TBD
TOTAL (excl. VAT) | [5 empty] | TBD
NOTES:
1. All prices in THB. USD/JPY options available on request.
2. Items marked TBD require answers to Technical Questions sheet before final pricing.
3. Lead times are from order placement and receipt of signed PO.
4. This quotation is valid for 30 days from issue date.
5. Existing test instruments (1x KIKUSUI, 1x PCAN, 1x Trace32) not included in Section B cost.
6. Software items in Section C assume U-Shin provides full FCT test requirements and Lauterbach script access.
7. PLC program (C-07) to be agreed — can be U-Shin internal or external vendor scope.